## Slide 1
eTransformation PMO Recommended
Minimum Steering Committee Elements
Version 2- Mar 2020
PMO Team

## Slide 2: Disclaimer
These are guidelines in-order to assist the Ministry teams.
The parameters and components for Steering Committee reporting should be considered as the Minimum set of reporting elements.
Ministries does not have to restrict themselves only to the defined set of parameters.
If more parameters are needed then then Ministry and Vendor can discuss and agree on the same.
ITA may also revise and update these norms from time to time.

## Slide 3: Steering Committee Constitution Guidelines
Steering Committee should be ideally chaired by the Ministry that own the initiative .
Steering Committee members should ideally be from all the stakeholders who are part of the Project.
Steering Committee should ideally meet on every month.
Once the Steering committee is constituted then it is recommended to block the calendars of all the members for the duration of the project. (PMO Tool- Meeting Planner Template can be used to plan).

## Slide 4: Steering Committee Meeting preparation
The Monthly report should be produced in Power Point format.
The current month report should be prepared 5 days before the date of Steering Committee.
The report need to be discussed with the members of the Project team to ensure alignment and points being covered.
No Operational topics should be covered in the Steering Committee. Only key decisions expected and where there is a bottleneck that is unable to be solved at Project Level only need to be presented in Steering Committee.
A copy of the finalized slide need to be emailed to pmo@ita.gov.om for reference and records.

## Slide 5: Steering Committee Mandate
Setting the scope, objectives and directions of the project.
Follow up progress of the project as a whole.
Allocation of the project budget and resources.
Approval and follow-up of project funds.
Final approval of the completion of the project and acceptance.
Decisions regarding the change requests presented by the Project team.
Finding solutions to any disputes between the parties to the project.
Making the final decision regarding the strategic and financial issues related to the project.

## Slide 6: MINIMUM SC ELEMENTS- Reporting TEMPLATE

## Slide 7: Overall Schedule
A graphical representation of the overall project schedule should be presented.
The graphical representation should show , in which stage of the schedule is the project currently.
The team can make use of the templates provided or use the template as long as the same is graphical.
PMO Guidance/ Recommendation
In the first Steering Committee, present and re-confirm and validate the timelines and scope.
Convey that changes to agreed timelines and scope will need changes to contract as well as the change request process.
The overall schedule slide once finalized should NOT be changed. PMO mandates that the same graphical view is show cased throughout the project.

## Slide 8: Overall Schedule- BC
STAGE 1
STAGE 2
STAGE 3
This is a sample text. Insert your desired text here.
This is a sample text. Insert your desired text here.
This is a sample text. Insert your desired text here.
1 year
2.5 year
1 year

## Slide 9: Overall Schedule- SI
STAGE 1
STAGE 2
STAGE 3
This is a sample text. Insert your desired text here.
This is a sample text. Insert your desired text here.
This is a sample text. Insert your desired text here.
1 year
2.5 year
1 year

## Slide 10: Planned Steering Committee Schedule for the Project
A calendar with all the planned dates for the Steering Committee.
It should be informed that Project team will inform the Steering committee member office to book the calendars for the whole duration of the project.
Steering Committee member support needed to inform his office the need to book the calendars and to ensure participation as much as possible in the planned meetings.

## Slide 11: Updates to the key action items from last steering committee
Inputs from last steering committee and action taken

## Slide 12: Project Achievements
Statistics if the project has gone live.
Phases of projects that are completed etc

## Slide 13: Planned activities for coming month
An overview of the key activities that are planned in the coming month and before the next steering committee.
Any Support needed from the Steering Committee for the planned activities.

## Slide 14: Transformation Mandate Status
Integrated with ROP, MOCI etc.
Integrations
02
Supports Online payment (If applicable).
Online Payment
03
Backend operations are Fully Automated.
Fully Automated
05
With no visit required to the Office.
Service Output is also provided Online
0 Visits
04
Use PKI for Authentication ( and or Mobile PKI)
PKI Login
01
State the Progress
Status
Highlight how many process can be achieved with 0 visit and how many cannot and if the process needs visit reasons should be highlighted
State the Progress
State the Progress
State the Progress

## Slide 15: SME/ Omanisation Status
Team need to highlight the following
  Name of SME Engaged
  Scope of Work carried out by SME
  No of Omanis part of the Project
  Roles Handled by Omanis

## Slide 16: Risks/ Challenges
Do NOT copy and paste the project risk and challenges sheet.
Only issues and risks which needs Steering Committee focus and direction only should be showcases.
For each of the challenge a recommendation to overcome the challenge should be stated by the team so that Steering Committee can endorse the recommendations.

## Slide 17: Decisions expected with numbering
PMO Guidelines and Recommendation
This should be the last slide of the presentation.
Approach of asking for directions need NOT be there.
All the detailed discussions and analysis should be completed at the Project level.
The final option which the team has agreed and expect should be presented for Steering Committee for endorsement.
Whoever can present confidently and convince should only present.

## Slide 18
Thank You