## BC
This document is a property of Digital Transformation PMO at Ministry of Technology and Communications. These guidance has been developed based on the expertise and involvement of the PMO Members in Various Digital Transformation Projects. No part of these checklist may be reproduced or transmitted in any form or by any means, electronic or mechanical, including photocopying, recording or by any information storage and retrieval system, without permission in writing from Digital Transformation PMO.
| Start Date | 2021-02-15 |  |  | 2018-02-26
| Milestone | Start | End | Average |  | Plan | Actual
| Service Catalog Development | 2021-02-15 | 2021-03-01 | 14 |  | 14 | 14
| Assess Business Processes (As-Is) | 2021-03-02 | 2021-05-07 | 66 |  | 58 | 66
| Review the As-Is IT Landscape | 2021-05-08 | 2021-07-01 | 54 |  | 48 | 54
| Align to e.oman Strategy and Core Infrastructure | 2021-07-02 | 2021-07-27 | 25 |  | 25 | 25
| Define the To-Be IT Architecture | 2021-07-28 | 2021-09-20 | 54 |  | 42 | 54
| Recommend the To Be Business Processes and Enhancements | 2021-09-21 | 2021-12-05 | 75 |  | 63 | 75
| Content Management & Customer Digitization Strategy | 2021-12-06 | 2022-01-15 | 40 |  | 40 | 40
| Develop KPI and SLA framework | 2022-01-16 | 2022-03-09 | 52 |  | 31 | 52
Formulas:
Start = [End, row above]+1
End = [Start]+[Average]

## RFP
Start Date | 2021-02-15
Milestone | Start | End | Average
RFP Draft | 2021-02-15 | 2021-03-19 | 32
RFP Review and Finalization | 2021-03-20 | 2021-04-27 | 38
Budget Confirmation | 2021-04-28 | 2021-06-19 | 52
Internal Tender Committee Process and Approval | 2021-06-20 | 2021-07-04 | 14
RFP Floating Administrative Process | 2021-07-05 | 2021-07-28 | 23
RFP Floating Date | 2021-07-29 | 2021-08-05 | 7
Formulas:
Start = [End, row above]+1
End = [Start]+[Average]

## PE
Start Date | 2017-09-30
Milestone | Start | End | Average | Actual | plan
Tender Announcement date | 2017-09-30 | 2017-10-03 | 3 | 3 | 3
Tender Opening date | 2017-10-04 | 2017-10-06 | 2 | 7 | 2
Technical Proposal evaluation | 2017-10-07 | 2017-12-02 | 56 | 77 | 56
Management Approval-Technical Evaluation | 2017-12-03 | 2017-12-09 | 6 | 70 | 6
Commercial Proposals Opening | 2017-12-10 | 2017-12-27 | 17 | 89 | 17
Commercial Proposals Evaluation | 2017-12-28 | 2018-02-04 | 38 | 106 | 38
Management Approval- Commercial and Technical Proposal | 2018-02-05 | 2018-03-12 | 35 | 102 | 35
157
Formulas:
Start = [End, row above]+1
End = [Start]+[Average]

## Contract
Start Date | 2017-11-01
Milestone | Start | End | Average
Statement of work | 2017-11-01 | 2017-12-07 | 36
Negotiation Process | 2017-12-08 | 2018-02-09 | 63
Contract Finalization | 2018-02-10 | 2018-04-27 | 76
Formulas:
Start = [End, row above]+1
End = [Start]+[Average]