## Business Consultancy (hidden)
Basic | Full | Theme | Business process/Module | Milestone | TO-BE process | Change management | Legal | Follow-up/PM | Total
y | y | Availability | Define overall vision for Availability theme | 1. Milestone | 0 | 15 | 0 | 0 | 15
y | y | Availability | BP1 - Access to CR information | 1. Milestone | 5 | 5 | 3 | 5 | 18
|  | Availability | BP2 - Access to trademark information |  | Covered in technical scope of work |  |  |  | 0
n | y | Availability | BP3 - Publish public announcement | 1. Milestone | 5 | 3 | 4 | 2 | 14
n | y | Availability | BP4 - Publish public announcement by editor | 1. Milestone | 2 | 3 | 0 | 2 | 7
|  | Availability | BP5 - Search public announcements |  | Covered in technical scope of work |  |  |  | 0
|  | Availability | BP8 - Digitalization of submitted paper documents |  | Covered in technical scope of work |  |  |  | 0
n | y | Availability | BP9 - Report debt via eCR | 4. Milestone | 8 | 5 | 3 | 4 | 20
n | y | Availability | BP10 - Reporting about debt via OSS front office. | 4. Milestone | 2 | 0 | 0 | 2 | 4
n | y | Availability | BP11 - Cancellation of debt via eCR | 4. Milestone | 2 | 0 | 3 | 2 | 7
|  | Availability | BP12 - Cancellation of debt via OSS front office |  | Duplicate of BP11 |  |  |  | 0
|  | Availability | BP13 - Search debt |  | Covered in technical scope of work |  |  |  | 0
y | y | Availability | BP14 - My CR | 2. Milestone | 10 | 8 | 2 | 5 | 25
y | y | Availability | BP15 - Access to Back Office System | 1. Milestone | 1 | 4 | 5 | 4 | 14
y | y | Availability | BP16 - Use of Task Calendar via eCR | 2. Milestone | 3 | 6 | 1 | 4 | 14
y | y | Commercial Registration | Define overall vision for CR theme | 1. Milestone | 0 | 15 | 0 | 0 | 15
y | y | Commercial Registration | BP17 - Submission of new CR registration application via eCR | 1. Milestone | 12 | 22 | 5 | 15 | 54
y | y | Commercial Registration | BP18 - New CR registration application proceeding in Back Office System | 2. Milestone | 12 | 15 | 0 | 10 | 37
y | y | Commercial Registration | BP19 - Submission of new CR registration application by service provider | 2. Milestone | 10 | 5 | 0 | 5 | 20
y |  | Commercial Registration | BP20 - New CR registration application proceeding in Back Office System |  | Duplicated from BP18 |  |  |  | 0
y | y | Commercial Registration | BP21 - Submission of new CR registration application via OSS front office counter | 2. Milestone | 1 | 3 | 0 | 6 | 10
|  | Commercial Registration | BP22 - Closing of name reservation and renewal of reserved name |  | Included in BP17, BP19, BP21 | 0 | 0 | 0 | 0
|  | Commercial Registration | BP23 - Name verification process |  | Included in BP17, BP19, BP21 | 0 | 0 | 0 | 0
y | y | Update CR | BP24 - Update CR information via eCR | 3. Milestone | 18 | 27 | 4 | 18 | 67
|  | Update CR | BP25 - Automatic registration of changes in Back Office System |  | Included in BP24 | 0 | 0 | 0 | 0
y | y | Update CR | BP26 - Proceeding of update application in Back Office System | 3. Milestone | 12 | 15 | 0 | 10 | 37
y | y | Update CR | BP27 - Ownership transfer | 3. Milestone | 6 | 12 | 7 | 10 | 35
y | y | Update CR | BP28 - Automated CR information update requests from other government registers/information systems. | 4. Milestone | 4 | 10 | 5 | 8 | 27
y | y | Update CR | BP29 - Liquidation CR via eCR | 4. Milestone | 8 | 12 | 7 | 10 | 37
|  | Update CR | BP30 - Cancellation CR via eCR |  | Included in BP29 | 0 | 0 | 0 | 0
n | y | Update CR | BP31 - Submitting annual report via eCR | 4. Milestone | 14 | 25 | 6 | 18 | 63
n | y | Update CR | BP32 - Verification and processing of annual report in Back Office System | 4. Milestone | 14 | 22 | 3 | 15 | 54
|  | Update CR | BP33 - Supervision regarding submission of annual report | 4. Milestone | Included in BP32 | 0 | 0 | 0 | 0
|  | Update CR | BP34 - Penalization | 5. Milestone | Included in BP32 | 0 | 0 | 0 | 0
y | y | Update CR | BP35 - Register new commercial establishment mortgage. | 4. Milestone | 8 | 10 | 5 | 11 | 34
y | y | Update CR | BP36 - Update commercial establishment’s mortgage. | 4. Milestone | 5 | 7 | 3 | 8 | 23
y | y | Update CR | BP37 - Cancel commercial establishment mortgage | 4. Milestone | 3 | 4 | 2 | 4 | 13
y | y | Licensing | Define overall vision for licensing theme | 2. Milestone | 0 | 25 | 0 | 0 | 25
y | y | Licensing | BP38 - Submission of notice of economic activities | 2. Milestone | 60 | 60 | 20 | 20 | 160
y | y | Licensing | BP39 - Submission of application for activity licence | 3. Milestone | 60 | 60 | 20 | 20 | 160
y | y | Licensing | BP40 - Adjudication of application for activity licence | 3. Milestone | 40 | 30 | 5 | 10 | 85
y | y | Licensing | BP41 - Modification of notice of economic activities | 2. Milestone | 40 | 30 | 5 | 10 | 85
y | y | Licensing | BP42 - Modification of activity licence | 3. Milestone | 40 | 30 | 5 | 10 | 85
|  | Licensing | BP43 - Place of activity trade |  | Covered in technical scope of work |  |  |  | 0
y | y | Licensing | BP44 - Cancellation of notice of economic activities | 3. Milestone | 15 | 5 | 2 | 5 | 27
y | y | Licensing | BP45 - Cancellation of activity licence | 3. Milestone | 15 | 5 | 2 | 5 | 27
y | y | Licensing | BP46 - Fines registration process | 4. Milestone | 5 | 3 | 2 | 4 | 14
|  | Licensing | BP47 - ISIC Maintenance process |  | Covered in technical scope of work |  |  |  | 0
y | y | Availability | M12 Statistics and Reports Module - Define performance indicators for Availability | 2. Milestone | 0 | 10 | 0 | 20 | 30
y | y | Commercial Registration, Update CR | M12 Statistics and Reports Module - Define performance indicators for CR | 4. Milestone | 0 | 10 | 0 | 20 | 30
y | y | Licensing | M12 Statistics and Reports Module - Define performance indicators for Licensing | 4. Milestone | 0 | 10 | 0 | 30 | 40
n | y | Availability | FN37 Search Official Gazette - Content creation and upload procedures | 5. Milestone | 0 | 15 | 0 | 5 | 20
n | y | Update CR | Create XBRL taxonomy phase I - define annual report strucutre and validation rules based on MoCI requirements | 2. Milestone | 50 | 0 | 5 | 20 | 75
n | y | Update CR | Create XBRL taxonomy phase II - Create 1st XBRL taxonomy version based on previous phase deliverables | 3. Milestone | 50 | 0 | 5 | 0 | 55
n | y | Update CR | Create XBRL taxonomy phase III - Involve CMA; SGT and OCCI and collect their additional requirements for annual reporting | 4. Milestone | 50 | 0 | 5 | 0 | 55
n | y | Update CR | Create XBRL taxonomy phase IV Create 2nd version of XBRL taxonomy based on previous phase deliverables. | 5. Milestone | 50 | 0 | 5 | 0 | 55
n | y | Update CR | XBRL awareness | 2. Milestone | 0 | 20 | 0 | 0 | 20
[5 empty] | 640 | 566 | 149 | 357 | 1712

## General tasks (hidden)
Basic | Full | Module | Sub-system | Requirement | Task | Milestone | Cross reference | Analysis | UI design | Development | Testing | Total |  | Grand total
y | y | Person Managment Module | OSS | GR1 Remove Manual Investor Data Entry | Load data from ROP | 2. Milestone |  | 4 | 0 | 9 | 3 | 16 |  | Basic | Full
y | y | Person Managment Module |  | GR1 Remove Manual Investor Data Entry | Restrict any changes of data loaded from ROP via OSS system | 2. Milestone |  | 30 | 4 | 45 | 15 | 94 |  | 2042.5 | 3033.5
y | y | Person Managment Module |  | GR1 Remove Manual Investor Data Entry | List persons who don’t have record in ROP (foreign investors) | 2. Milestone |  | 4 | 2 | 13 | 3 | 22
y | y | Person Managment Module |  | GR1 Remove Manual Investor Data Entry | Update foreign investors data | 2. Milestone |  | 4 | 1 | 9 | 2 | 16
y | y | Person Managment Module |  | GR1 Remove Manual Investor Data Entry | Merge foreign investor records | 2. Milestone |  | 2 | 1 | 8 | 2 | 13
y | y | Person Managment Module |  | GR1 Remove Manual Investor Data Entry | Merge foreign investor with ROP data | 2. Milestone |  | 2 | 1 | 7 | 2 | 12
y | y | Person Managment Module | Data exchange | GR1 Remove Manual Investor Data Entry |  |  |  | Efforts under OSS simplification |  |  |  | 0
y | y |  |  | GR13 Screen Navigation | User experience | 2. Milestone |  | 120 | 10 | 0 | 0 | 130
y | y |  |  | GR13 Screen Navigation | Branding | 1. Milestone |  | 30 | 20 | 0 | 0 | 50
y | y |  |  | GR13 Screen Navigation | Design | 1. Milestone |  | 25 | 40 | 40 | 20 | 125
y | y | Identification module |  | GR11 Single Sign On |  |  |  | SSO is already implemented and no additonal effort |  |  |  | 0
y | y | Identification module |  | FN1 PKI authentication | PKI for webapplications |  |  | No additional efforts |  |  |  | 0
y | y | Identification module |  | FN1 PKI authentication | PKI for mobile application | 3. Milestone |  | Efforts under Mobile Application |  |  |  | 0
y | y | Authorization module | eCR | GR12 Authorization and Delegation | List of authorized users | 3. Milestone |  | 5 | 2 | 9 | 2 | 18
y | y | Authorization module | eCR | GR12 Authorization and Delegation | View details of authorized user | 3. Milestone |  | 4 | 1 | 9 | 2 | 16
y | y | Authorization module | eCR | GR12 Authorization and Delegation | Add authorized user | 3. Milestone |  | 4 | 1 | 10 | 2 | 17
y | y | Authorization module | eCR | GR12 Authorization and Delegation | Change privileges for authorized users | 3. Milestone |  | 3 | 1 | 8 | 1 | 13
y | y | Authorization module | eCR | GR12 Authorization and Delegation | Remove authorized user | 3. Milestone |  | 2 | 0.5 | 6 | 1 | 9.5
y | y | Authorization module | eCR | GR12 Authorization and Delegation | Change organization | 3. Milestone |  | 5 | 1 | 12 | 2 | 20
y | y | Authorization module | OSS | GR12 Authorization and Delegation | List of authorized users | 3. Milestone |  | 1 | 0 | 2 | 1 | 4
y | y | Authorization module | OSS | GR12 Authorization and Delegation | View details of authorized user | 3. Milestone |  | 0 | 0 | 0 | 0 | 0
y | y | Authorization module | OSS | GR12 Authorization and Delegation | Add authorized user | 3. Milestone |  | 1 | 0 | 2 | 1 | 4
y | y | Authorization module | OSS | GR12 Authorization and Delegation | Change privileges for authorized users | 3. Milestone |  | 0 | 0 | 0 | 0 | 0
y | y | Authorization module | OSS | GR12 Authorization and Delegation | Remove authorized user | 3. Milestone |  | 0 | 0 | 0 | 0 | 0
n | y | Digital stamping |  | FN2 PKI electronic signature | Sign document with smart-card | 3. Milestone |  | 25 | 5 | 45 | 10 | 85
n | y | Digital stamping |  | FN4 Electronic stamp | Digital stamp | 3. Milestone |  | 30 | 0 | 31 | 10 | 71
n | y | Digital stamping |  | FN2 PKI electronic signature | Validate signature | 3. Milestone |  | 7 | 3 | 12 | 3 | 25
y | y | Payment module |  | FN5 Payment calculator | Simulators |  |  | Efforts under OSS simplification |  |  |  | 0
y | y | Payment module |  | FN6 Payment statistics | Online payment | 2. Milestone |  | 4 | 2 | 10 | 3 | 19
y | y | Payment module |  | FN6 Payment statistics | Register payment in front-office | 2. Milestone |  | 12 | 3 | 19 | 3 | 37
y | y | Payment module |  | FN6 Payment statistics | Print receipt for received payment | 2. Milestone |  | 4 | 2 | 9 | 2 | 17
y | y | Payment module |  | FN6 Payment statistics | List all received payments and refunds | 2. Milestone |  | 12 | 3 | 20 | 4 | 39
y | y | Payment module |  | FN6 Payment statistics | View payment details | 2. Milestone |  | 3 | 1 | 9 | 2 | 15
y | y | Payment module |  | FN7 Submit refund application | Register refund application | 5. Milestone |  | 9 | 3 | 16 | 3 | 31
y | y | Payment module |  | FN7 Submit refund application | Process refund application | 5. Milestone |  | 12 | 3 | 24 | 8 | 47
y | y | Payment module |  | FN7 Submit refund application | Pay refund | 5. Milestone |  | 3 | 1 | 8 | 1 | 13
y | y | Payment module |  | FN6 Payment statistics | My payments | 2. Milestone |  | 5 | 2 | 14 | 4 | 25
n | y | WSRP Bridge | eCR | 3.3.1.4 MoCI to oman.om bridge | Establish connectivity between different environments | 6. Milestone |  | 15 | 0 | 10 | 5 | 30
n | y | WSRP Bridge | eCR | 3.3.1.4 MoCI to oman.om bridge | Configure producer | 6. Milestone |  | 10 | 0 | 20 | 10 | 40
n | y | WSRP Bridge | eCR |  | Create pages and layout on consumer side | 6. Milestone |  | Not included in the scope of work |  |  |  | 0
n | y | WSRP Bridge | eCR |  | Configure consumers | 6. Milestone |  | Not included in the scope of work |  |  |  | 0
n | y | WSRP Bridge | eCR |  | Define security at consumer end | 6. Milestone |  | Not included in the scope of work |  |  |  | 0
y | y |  |  | GR8 System Documentation | Functional documentation I | 1. Milestone |  | 60 | 0 | 0 | 0 | 60
n | y |  |  | GR8 System Documentation | Functional documentation II | 2. Milestone |  | 60 | 0 | 0 | 0 | 60
n | y |  |  | GR8 System Documentation | Functional documentation III | 3. Milestone |  | 60 | 0 | 0 | 0 | 60
n | y |  |  | GR8 System Documentation | Functional documentation IV | 4. Milestone |  | 60 | 0 | 0 | 0 | 60
n | y |  |  | GR8 System Documentation | Functional documentation V | 5. Milestone |  | 60 | 0 | 0 | 0 | 60
n | y |  |  | GR8 System Documentation | Functional documentation VI | 6. Milestone |  | 60 | 0 | 0 | 0 | 60
y | y |  |  | GR8 System Documentation | System architecture I | 1. Milestone |  | 20 | 0 | 120 | 0 | 140
n | y |  |  | GR8 System Documentation | System architecture II | 3. Milestone |  | 20 | 0 | 80 | 0 | 100
y | y |  |  | GR8 System Documentation | Build manual | 1. Milestone |  | 5 | 0 | 15 | 5 | 25
y | y |  |  | GR8 System Documentation | Build manual update I | 2. Milestone |  | 2 | 0 | 10 | 5 | 17
y | y |  |  | GR8 System Documentation | Build manual update II | 3. Milestone |  | 2 | 0 | 10 | 5 | 17
y | y |  |  | GR8 System Documentation | Build manual update III | 4. Milestone |  | 2 | 0 | 10 | 5 | 17
y | y |  |  | GR8 System Documentation | Build manual update IV | 5. Milestone |  | 2 | 0 | 10 | 5 | 17
y | y |  |  | GR8 System Documentation | Build manual update V | 6. Milestone |  | 2 | 0 | 10 | 5 | 17
y | y |  |  | GR8 System Documentation | Deployment manual | 1. Milestone |  | 5 | 0 | 10 | 0 | 15
y | y |  |  | GR8 System Documentation | Deployment manual update I | 2. Milestone |  | 2 | 0 | 5 | 0 | 7
y | y |  |  | GR8 System Documentation | Deployment manual update II | 3. Milestone |  | 2 | 0 | 5 | 0 | 7
y | y |  |  | GR8 System Documentation | Deployment manual update III | 4. Milestone |  | 2 | 0 | 5 | 0 | 7
y | y |  |  | GR8 System Documentation | Deployment manual update IV | 5. Milestone |  | 2 | 0 | 5 | 0 | 7
y | y |  |  | GR8 System Documentation | Deployment manual update V | 6. Milestone |  | 2 | 0 | 5 | 0 | 7
y | y |  |  | GR8 System Documentation | Test plans | 1. Milestone |  | 25 | 0 | 60 | 80 | 165
y | y |  |  | GR8 System Documentation | Test report I | 1. Milestone |  | 5 | 0 | 0 | 10 | 15
y | y |  |  | GR8 System Documentation | Test report II | 2. Milestone |  | 5 | 0 | 0 | 10 | 15
y | y |  |  | GR8 System Documentation | Test report III | 3. Milestone |  | 5 | 0 | 0 | 10 | 15
y | y |  |  | GR8 System Documentation | Test report IV | 4. Milestone |  | 5 | 0 | 0 | 10 | 15
y | y |  |  | GR8 System Documentation | Test report V | 5. Milestone |  | 5 | 0 | 0 | 10 | 15
y | y |  |  | GR8 System Documentation | Test report VI | 6. Milestone |  | 5 | 0 | 0 | 10 | 15
y | y |  |  | GR8 System Documentation | MO procedures | 2. Milestone |  | 20 | 0 | 40 | 10 | 70
y | y |  |  | GR8 System Documentation | MO procedures update I | 4. Milestone |  | 10 | 0 | 20 | 5 | 35
y | y |  |  | GR8 System Documentation | MO procedures update II | 6. Milestone |  | 10 | 0 | 20 | 5 | 35
y | y |  |  | GR14 Testing | Develop automated tests I | 3. Milestone |  | 5 | 0 | 60 | 0 | 65
y | y |  |  | GR14 Testing | Develop automated tests II | 4. Milestone |  | 5 | 0 | 60 | 0 | 65
n | y |  |  | GR14 Testing | Develop automated tests III | 5. Milestone |  | 5 | 0 | 60 | 0 | 65
n | y |  |  | GR14 Testing | Develop automated tests IV | 6. Milestone |  | 5 | 0 | 60 | 0 | 65
n | y |  |  | GR14 Testing | Develop automated tests V | 6. Milestone |  | 5 | 0 | 60 | 0 | 65
y | y |  |  | GR14 Testing | Run automated tests | 6. Milestone |  | 5 | 0 | 15 | 0 | 20
y | y |  |  | GR14 Testing | Stress testing II | 6. Milestone |  | 5 | 0 | 0 | 5 | 10
n | y |  |  | GR14 Testing | Stress testing I | 5. Milestone |  | 5 | 0 | 0 | 5 | 10
| y |  |  | GR10 Web Service Support |  |  |  | No effort, WS support part of architecture design |  |  |  | 0
y | y | Migration to new architecture | OSS | GR3 Reusability | Migration from EJB2 to EJB3 | 1. Milestone |  | 0 | 0 | 20 | 10 | 30
y | y | Migration to new architecture | OSS | GR3 Reusability | Split OSS project into modules | 1. Milestone |  | 0 | 0 | 10 | 5 | 15
y | y | Migration to new architecture | OSS | GR3 Reusability | Migration of Business and Persistence layer to Core Services | 2. Milestone |  | 0 | 0 | 20 | 10 | 30
y | y | Migration to new architecture | OSS | GR2 Matching Business Rules | Migration of OSS presentation layer I | 2. Milestone |  | 0 | 0 | 20 | 10 | 30
y | y | Migration to new architecture | OSS | GR2 Matching Business Rules | Migration of OSS presentation layer II | 3. Milestone |  | 0 | 0 | 20 | 10 | 30
y | y | Migration to new architecture | OSS | GR2 Matching Business Rules | Migration of OSS presentation layer III | 4. Milestone |  | 0 | 0 | 20 | 10 | 30
y | y | Migration to new architecture | OSS | GR2 Matching Business Rules | Migration of OSS presentation layer IV | 5. Milestone |  | 0 | 0 | 10 | 5 | 15
y | y |  |  | GR4 Code Compliance principles |  |  |  | Code compliance is enforced by architecture design |  |  |  | 0
n | y |  |  | GR5 Code Compliance Report | Create, run and deliver google pro code analytics report (eCR & OSS) | 6. Milestone |  | 0 | 0 | 5 | 0 | 5
y | y |  |  | GR6 Interface Compliance |  |  |  | For eCR & Mobile - included in functionality estimates; for OSS included in migration effort |  |  |  | 0
y | y |  |  | GR7 Code Documentation |  |  |  | Enforced by Nortal's internal software development process |  |  |  | 0
y | y |  |  | GR9 Interface Compliance Checks | Create, run and deliver interface compliance reports (eCR, OSS, Mobile App, Website) | 6. Milestone |  | 0 | 0 | 10 | 0 | 10
n | y | Form engine |  | FN3 Automated checks | Installation of form engine | 2. Milestone |  | 5 | 0 | 15 | 3 | 23
n | y | Form engine |  | FN3 Automated checks | Integration of form engine | 2. Milestone |  | 10 | 0 | 40 | 10 | 60
n | y | Form engine |  | FN3 Automated checks | Customization of form engine | 3. Milestone |  | 15 | 0 | 25 | 7 | 47
n | y | Form engine |  |  | Forms development |  |  | Included in tasks that require forms |  |  |  | 0
y | y | Workflow engine |  | FN3 Automated checks | Integration of Activi engine in core services | 2. Milestone |  | 0 | 0 | 10 | 5 | 15
y | y | Workflow engine |  | FN3 Automated checks | Integration of Activiti explorer in eCR and OSS | 2. Milestone |  | 0 | 0 | 20 | 10 | 30
y | y | Workflow engine |  | FN3 Automated checks | Customization of Activiti | 3. Milestone |  | 5 | 5 | 20 | 10 | 40
y | y | Workflow engine |  |  | Workflows development |  |  | Included in OSS simplification for functionalities that require workflows |  |  |  | 0
y | y | Rule engine |  | FN3 Automated checks | Integration of Drools in core services | 2. Milestone |  | 0 | 0 | 10 | 5 | 15
y | y | Rule engine |  | FN3 Automated checks | Integration of management console in OSS | 2. Milestone |  | 0 | 0 | 10 | 5 | 15
y | y | Rule engine |  |  | Creation of knowledge base |  |  | Included in OSS simplification for functionalities that require workflows |  |  |  | 0
n | y | OCR |  |  | Abby OCR license | 1. Milestone | [5 empty] | 0 | 300 | OMR
n | y | Statistics and reports module |  |  | Pentaho BI license | 1. Milestone | [5 empty] | 0 | 30000 | OMR
y | y |  |  |  | Activiti license | 1. Milestone | [5 empty] | 0 | 0 | OMR
y | y |  |  |  | Drools license | 1. Milestone | [5 empty] | 0 | 0 | OMR
n | y |  |  |  | Xwand license | 1. Milestone | [5 empty] | 0 | 2000 | OMR
n | y | Roll-out |  |  | Orbeon Gold (2 years) | 2. Milestone | [5 empty] | 0 | 13000 | OMR
Note on F21: Peeter Smitt: Only OSS specifs development is included (identifing user over the counter and selecing the organization)
Note on F30: Peeter Smitt: Only UI integration effort
Note on F44: Peeter Smitt: Effort includes sign-offs and handover
Note on F64: Peeter Smitt: Functional testing is include in task estimates. This is about stress tests and integration tests.
Note on F74: Peeter Smitt: Functional testing is included in task estimates
Note on F79: Peeter Smitt: Development of framework to run test automatically

## OSS Simplification (hidden)
Basic | Full | Theme | Module | Sub-system | Requirement | Use-case | Milestone | Cross reference | Analysis | UI design | Development | Testing | Total | Grand total
n | y | Availability | M1 Public announcements | eCR | FN34 Search public announcement | List of my announcements | 2. Milestone |  | 2 | 2 | 5 | 1 | 10 | Basic | Full
n | y | Availability | M1 Public announcements | eCR | FN34 Search public announcement | Display details of my announcements | 2. Milestone |  | 2 | 2 | 5 | 1 | 10 | 2469.5 | 5929
n | y | Availability | M1 Public announcements | eCR |  | Enter new announcement | 2. Milestone |  | 3 | 3 | 7 | 2 | 15
n | y | Availability | M1 Public announcements | eCR | FN36 Publish public announcement | Submit announcement for publishing | 2. Milestone |  | 2 | 1 | 5 | 1 | 9
n | y | Availability | M1 Public announcements | eCR | FN34 Search public announcement | List of announcements | 2. Milestone |  | 2 | 1 | 3 | 1 | 7
n | y | Availability | M1 Public announcements | eCR | FN34 Search public announcement | Display announcement | 2. Milestone |  | 1 | 1 | 3 | 1 | 6
n | y | Availability | M1 Public announcements | eCR | FN35 Search public announcement XML | Public announcements XML | 2. Milestone |  | 3 | 0 | 10 | 2 | 15
n | y | Availability | M1 Public announcements | OSS | FN43 Publish an announcement | Manage templates | 2. Milestone |  | 5 | 3 | 15 | 4 | 27
n | y | Availability | M1 Public announcements | OSS | FN43 Publish an announcement | Fees calculation | 2. Milestone |  | 3 | 2 | 7 | 3 | 15
n | y | Availability | M1 Public announcements | OSS | FN44 Search public announcement | List of announcements | 2. Milestone |  | 2 | 1 | 5 | 1 | 9
n | y | Availability | M1 Public announcements | OSS | FN43 Publish an announcement | Review submitted announcements | 2. Milestone |  | 4 | 2 | 8 | 3 | 17
n | y | Availability | M1 Public announcements | OSS | FN43 Publish an announcement | Enter announcement based on request | 2. Milestone |  | 2 | 1 | 5 | 1 | 9
n | y | Availability | M1 Public announcements | Data exchange |  | Register public announcement | 2. Milestone |  | 2 | 0 | 5 | 3 | 10
n | y | Availability | M1 Public announcements | Data exchange |  | Search public announcement | 2. Milestone |  | 2 | 0 | 5 | 3 | 10
n | y | Availability | M3 Communication and notification module | eCR |  | List of my notifications | 5. Milestone |  | 2 | 2 | 5 | 1 | 10
n | y | Availability | M3 Communication and notification module | eCR |  | List of all possible notifications | 5. Milestone |  | 4 | 2 | 5 | 2 | 13
n | y | Availability | M3 Communication and notification module | eCR |  | Subscribe/un-subscribe from notification | 5. Milestone |  | 5 | 3 | 10 | 3 | 21
n | y | Availability | M3 Communication and notification module | eCR |  | Notification preferences | 5. Milestone |  | 4 | 2 | 10 | 3 | 19
n | y | Availability | M3 Communication and notification module | OSS |  | Administration of topics | 5. Milestone |  | 4 | 2 | 10 | 3 | 19
n | y | Availability | M3 Communication and notification module | OSS |  | Administration of notification templates | 5. Milestone |  | 3 | 1 | 7 | 2 | 13
n | y | Availability | M3 Communication and notification module | Data exchange |  | Send notification | 5. Milestone |  | 2 | 0 | 8 | 3 | 13
n | y | Availability | M3 Communication and notification module | Data exchange |  | Send broadcast message | 5. Milestone |  | 2 | 0 | 9 | 3 | 14
n | y | Availability | M3 Communication and notification module | Data exchange |  | Integration with SMS GW | 5. Milestone |  | 4 | 0 | 12 | 2 | 18
n | y | Availability | M3 Communication and notification module | Data exchange |  | Integration with e-mail server | 5. Milestone |  | 3 | 0 | 6 | 2 | 11
y | y | Licensing | M4 Licence requirements management module(ISIC classification) | OSS | 6.4.2.1 Licensing | ISIC - Browse ISIC list | 3. Milestone |  | 5 | 2 | 15 | 4 | 26
y | y | Licensing | M4 Licence requirements management module(ISIC classification) | OSS | 6.4.2.1 Licensing | ISIC - Change list element | 3. Milestone |  | 3 | 1 | 5 | 2 | 11
y | y | Licensing | M4 Licence requirements management module(ISIC classification) | OSS | 6.4.2.1 Licensing | ISIC - Delete list element | 3. Milestone |  | 2 | 0.5 | 3 | 1 | 6.5
y | y | Licensing | M4 Licence requirements management module(ISIC classification) | OSS | 6.4.2.1 Licensing | ISIC - Discontinue list element | 3. Milestone |  | 2 | 0.5 | 3 | 1 | 6.5
y | y | Licensing | M4 Licence requirements management module(ISIC classification) | OSS | 6.4.2.1 Licensing | ISIC - Merge list element | 3. Milestone |  | 3 | 1 | 6 | 2 | 12
y | y | Licensing | M4 Licence requirements management module(ISIC classification) | OSS | 6.4.2.1 Licensing | ISIC - Move list element | 3. Milestone |  | 3 | 1 | 6 | 2 | 12
y | y | Licensing | M4 Licence requirements management module(ISIC classification) | OSS | 6.4.2.1 Licensing | ISIC - Add Section | 3. Milestone |  | 3 | 0.5 | 4 | 1 | 8.5
y | y | Licensing | M4 Licence requirements management module(ISIC classification) | OSS | 6.4.2.1 Licensing | ISIC - Add Division | 3. Milestone |  | 3 | 0.5 | 3 | 1 | 7.5
y | y | Licensing | M4 Licence requirements management module(ISIC classification) | OSS | 6.4.2.1 Licensing | ISIC - Add Group | 3. Milestone |  | 3 | 0.5 | 3 | 1 | 7.5
y | y | Licensing | M4 Licence requirements management module(ISIC classification) | OSS | 6.4.2.1 Licensing | ISIC - Add Class | 3. Milestone |  | 3 | 0.5 | 3 | 1 | 7.5
y | y | Licensing | M4 Licence requirements management module(ISIC classification) | OSS | 6.4.2.1 Licensing | ISCI - Audit trail | 3. Milestone |  | 7 | 2 | 19 | 5 | 33
n | y | Licensing | M4 Licence requirements management module(ISIC classification) | OSS | 6.4.2.1 Licensing | HS - Browse HS list | 4. Milestone |  | 4 | 2 | 13 | 4 | 23
n | y | Licensing | M4 Licence requirements management module(ISIC classification) | OSS | 6.4.2.1 Licensing | HS - Change list element | 4. Milestone |  | 3 | 1 | 5 | 2 | 11
n | y | Licensing | M4 Licence requirements management module(ISIC classification) | OSS | 6.4.2.1 Licensing | HS - Delete list element | 4. Milestone |  | 2 | 0.5 | 3 | 1 | 6.5
n | y | Licensing | M4 Licence requirements management module(ISIC classification) | OSS | 6.4.2.1 Licensing | HS - Discontinue HS element | 4. Milestone |  | 2 | 0.5 | 3 | 1 | 6.5
n | y | Licensing | M4 Licence requirements management module(ISIC classification) | OSS | 6.4.2.1 Licensing | HS - Move HS element | 4. Milestone |  | 3 | 1 | 6 | 2 | 12
n | y | Licensing | M4 Licence requirements management module(ISIC classification) | OSS | 6.4.2.1 Licensing | HS - Add Section | 4. Milestone |  | 3 | 0.5 | 3 | 1 | 7.5
n | y | Licensing | M4 Licence requirements management module(ISIC classification) | OSS | 6.4.2.1 Licensing | HS - Add Chapter | 4. Milestone |  | 3 | 0.5 | 3 | 1 | 7.5
n | y | Licensing | M4 Licence requirements management module(ISIC classification) | OSS | 6.4.2.1 Licensing | HS - Audit trail | 4. Milestone |  | 6 | 2 | 15 | 4 | 27
n | y | Licensing | M4 Licence requirements management module(ISIC classification) | OSS | 6.4.2.1 Licensing | ISIC2HS - Browse mappings | 4. Milestone |  | 5 | 3 | 23 | 7 | 38
n | y | Licensing | M4 Licence requirements management module(ISIC classification) | OSS | 6.4.2.1 Licensing | ISIC2HS - Remove mapping | 4. Milestone |  | 3 | 1 | 8 | 2 | 14
n | y | Licensing | M4 Licence requirements management module(ISIC classification) | OSS | 6.4.2.1 Licensing | ISIC2HS - Add mapping | 4. Milestone |  | 3 | 1 | 9 | 3 | 16
n | y | Licensing | M4 Licence requirements management module(ISIC classification) | OSS | 6.4.2.1 Licensing | ISIC2HS - Audit trail | 4. Milestone |  | 7 | 2 | 19 | 5 | 33
n | y | Licensing | M6 Licence Processing and Management module | eCR | FN20 Apply for licence/notice of economic activities | License/notice simulator | 5. Milestone |  | 20 | 7 | 67 | 15 | 109
n | y | Licensing | M6 Licence Processing and Management module | eCR | FN20 Apply for licence/notice of economic activities | New license application | 6. Milestone |  | 10 | 5 | 40 | 10 | 65
n | y | Licensing | M6 Licence Processing and Management module | eCR | FN22 Modify licence/notice of economic activities | Application for changing license | 6. Milestone |  | 10 | 5 | 20 | 5 | 40
n | y | Licensing | M6 Licence Processing and Management module | eCR |  | Submit license application | 6. Milestone |  | 3 | 1 | 5 | 1 | 10
n | y | Licensing | M6 Licence Processing and Management module | eCR |  | View license processing status | 6. Milestone |  | 4 | 2 | 11 | 3 | 20
n | y | Licensing | M6 Licence Processing and Management module | eCR | FN22 Modify licence/notice of economic activities | Renew license | 6. Milestone |  | 7 | 3 | 21 | 5 | 36
n | y | Licensing | M6 Licence Processing and Management module | eCR | FN21 My licences | My licenses | 6. Milestone |  | 3 | 1 | 13 | 3 | 20
n | y | Licensing | M6 Licence Processing and Management module | eCR | FN23 Cancel licence/notice of economic activities | Cancel license | 6. Milestone |  | 4 | 1 | 9 | 2 | 16
n | y | Licensing | M6 Licence Processing and Management module | eCR |  | Pay fine | 6. Milestone |  | 2 | 1 | 5 | 2 | 10
n | y | Licensing | M6 Licence Processing and Management module | eCR | FN24 Licence statistics | License report | 6. Milestone |  | 4 | 2 | 13 | 3 | 22
n | y | Licensing | M6 Licence Processing and Management module | eCR | FN25 ISIC search | ISIC Browser | 6. Milestone |  | 5 | 2 | 16 | 4 | 27
n | y | Licensing | M6 Licence Processing and Management module | OSS | 6.4.2.1 Licensing | License definition - General information | 4. Milestone |  | 4 | 1 | 14 | 3 | 22
n | y | Licensing | M6 Licence Processing and Management module | OSS | 6.4.2.1 Licensing | License definition - Requirements | 4. Milestone |  | 20 | 5 | 80 | 15 | 120
n | y | Licensing | M6 Licence Processing and Management module | OSS | 6.4.2.1 Licensing | License definition - Application form | 4. Milestone |  | 10 | 4 | 29 | 9 | 52
n | y | Licensing | M6 Licence Processing and Management module | OSS | 6.4.2.1 Licensing | License definition - Related documents | 4. Milestone |  | 4 | 1 | 13 | 3 | 21
n | y | Licensing | M6 Licence Processing and Management module | OSS | 6.4.2.1 Licensing | License definition - Fees calculation module | 4. Milestone |  | 4 | 1 | 15 | 5 | 25
n | y | Licensing | M6 Licence Processing and Management module | OSS | 6.4.2.1 Licensing | License definition - Application workflow | 4. Milestone |  | 4 | 2 | 25 | 10 | 41
n | y | Licensing | M6 Licence Processing and Management module | OSS | 6.4.2.1 Licensing | License definition - License certificate | 4. Milestone |  | 3 | 1 | 10 | 3 | 17
n | y | Licensing | M6 Licence Processing and Management module | OSS | 6.4.2.1 Licensing | License definition - License/notice coverage report | 4. Milestone |  | 5 | 2 | 19 | 4 | 30
n | y | Licensing | M6 Licence Processing and Management module | OSS | 6.4.2.1 Licensing | License processing - Task list | 4. Milestone |  | 3 | 1 | 14 | 4 | 22
n | y | Licensing | M6 Licence Processing and Management module | OSS | 6.4.2.1 Licensing | License processing - Human task forms (5 screens) | 4. Milestone |  | 8 | 2 | 40 | 20 | 70
n | y | Licensing | M6 Licence Processing and Management module | OSS | 6.4.2.1 Licensing | License processing - Human task forms (20 screens) | 5. Milestone |  | 32 | 8 | 140 | 60 | 240
n | y | Licensing | M6 Licence Processing and Management module | OSS | 6.4.2.1 Licensing | License processing - Execution of automated tasks | 4. Milestone |  | 13 | 0 | 27 | 8 | 48
n | y | Licensing | M6 Licence Processing and Management module | OSS | 6.4.2.1 Licensing | License processing - Progress monitoring | 4. Milestone |  | 5 | 2 | 14 | 4 | 25
n | y | Licensing | M6 Licence Processing and Management module | OSS | 6.4.2.1 Licensing | Supervision - Register fine | 5. Milestone |  | 4 | 1 | 9 | 3 | 17
n | y | Licensing | M6 Licence Processing and Management module | OSS | 6.4.2.1 Licensing | Supervision - List fines | 5. Milestone |  | 3 | 1 | 7 | 2 | 13
n | y | Licensing | M6 Licence Processing and Management module | OSS | 6.4.2.1 Licensing | Supervision - Edit fine | 5. Milestone |  | 2 | 0.5 | 5 | 2 | 9.5
n | y | Licensing | M6 Licence Processing and Management module | OSS | 6.4.2.1 Licensing | Supervision - Cancel fine | 5. Milestone |  | 2 | 0.5 | 5 | 1 | 8.5
n | y | Licensing | M6 Licence Processing and Management module | OSS | 6.4.2.1 Licensing | Supervision - Pay fine | 5. Milestone |  | 1 | 0 | 5 | 2 | 8
n | y | Licensing | M6 Licence Processing and Management module | OSS | 6.4.2.1 Licensing | Supervision - Send debt information to debt register | 5. Milestone |  | 3 | 0 | 8 | 2 | 13
n | y | Licensing | M6 Licence Processing and Management module | Data exchange | 7.5.7 Data exchange with different registers regarding licenses | Publish task list | 5. Milestone |  | 5 | 0 | 14 | 3 | 22
n | y | Licensing | M6 Licence Processing and Management module | Data exchange | 7.5.7 Data exchange with different registers regarding licenses | Publish task details | 5. Milestone |  | 5 | 0 | 13 | 3 | 21
n | y | Licensing | M6 Licence Processing and Management module | Data exchange | 7.5.7 Data exchange with different registers regarding licenses | Submit task processing results | 5. Milestone |  | 7 | 0 | 19 | 5 | 31
n | y | Availability | M7 Debt module | OSS | FN40 Report debt | Register debt | 5. Milestone |  | 3 | 1 | 9 | 1 | 14
n | y | Availability | M7 Debt module | OSS | FN41 Search debt | Search for debt | 5. Milestone |  | 3 | 1 | 12 | 1 | 17
n | y | Availability | M7 Debt module | OSS | FN41 Search debt | Display debt record | 5. Milestone |  | 3 | 1 | 11 | 1 | 16
n | y | Availability | M7 Debt module | OSS | FN31 Cancel debt | Cancel debt record | 5. Milestone |  | 2 | 1 | 6 | 1 | 10
n | y | Availability | M7 Debt module | eCR | FN30 Report debt | Register debt | 5. Milestone |  | 1 | 0.5 | 5 | 1 | 7.5
n | y | Availability | M7 Debt module | eCR | FN29 Search debt | Search for debt | 5. Milestone |  | 1 | 0.5 | 5 | 1 | 7.5
n | y | Availability | M7 Debt module | eCR | FN29 Search debt | Display debt record | 5. Milestone |  | 1 | 0.5 | 5 | 1 | 7.5
n | y | Availability | M7 Debt module | eCR | FN31 Cancel debt | Cancel debt record | 5. Milestone |  | 1 | 0.5 | 3 | 1 | 5.5
n | y | Availability | M7 Debt module | Data exchange | 7.5.6 Data exchange with debt register | Register dept | 5. Milestone |  | 5 | 0 | 17 | 3 | 25
n | y | Availability | M7 Debt module | Data exchange | 7.5.6 Data exchange with debt register | Search for dept | 5. Milestone |  | 5 | 0 | 12 | 2 | 19
n | y | Availability | M7 Debt module | Data exchange | 7.5.6 Data exchange with debt register | Cancel dept | 5. Milestone |  | 3 | 0 | 10 | 1 | 14
n | y | Availability | M8 Trademarks module | eCR | FN32 Search trademark | Link to ROMARIN | 1. Milestone |  | 3 | 0.5 | 4 | 1 | 8.5
n | y | Availability | M8 Trademarks module | eCR | FN33 Search trademark XML | Not achivable | 2. Milestone |  | 0 | 0 | 0 | 0 | 0
n | y | Availability | M8 Trademarks module | OSS | FN42 Trademark search | Search trademark | 2. Milestone |  | 3 | 0.5 | 4 | 1 | 8.5
n | y | Availability | M8 Trademarks module | OSS | FN42 Trademark search | Trademark registration details | 2. Milestone |  | 3 | 0.5 | 4 | 1 | 8.5
n | y | Availability | M8 Trademarks module | Data exchange | 7.5.4 Data exchange with trademark register (MOCI Trademark Department) | Not achivable | 2. Milestone |  | 0 | 0 | 0 | 0 | 0
n | y | All themes | M12 Statistics and Reports Module | eCR |  | ETL - Define extraction targets | 5. Milestone |  | 40 | 0 | 10 | 0 | 50
n | y | All themes | M12 Statistics and Reports Module | eCR |  | ETL - Define extraction scope | 5. Milestone |  | 40 | 0 | 10 | 10 | 60
n | y | All themes | M12 Statistics and Reports Module | eCR |  | ETL - Extract data | 5. Milestone |  | 15 | 0 | 15 | 5 | 35
n | y | All themes | M12 Statistics and Reports Module | eCR |  | ETL - Transformation sripts | 5. Milestone |  | 5 | 0 | 0 | 5 | 10
n | y | All themes | M12 Statistics and Reports Module | eCR |  | ETL - Error handling | 5. Milestone |  | 30 | 0 | 5 | 10 | 45
n | y | All themes | M12 Statistics and Reports Module | eCR |  | OLAP - Define fact tables | 6. Milestone |  | 15 | 0 | 0 | 5 | 20
n | y | All themes | M12 Statistics and Reports Module | eCR |  | OLAP - Configure dimensions | 6. Milestone |  | 30 | 0 | 0 | 5 | 35
n | y | All themes | M12 Statistics and Reports Module | eCR |  | OLAP - Configure hierarchies | 6. Milestone |  | 10 | 0 | 0 | 3 | 13
n | y | All themes | M12 Statistics and Reports Module | eCR |  | OLAP - Configure shared dimension | 6. Milestone |  | 10 | 0 | 0 | 5 | 15
n | y | All themes | M12 Statistics and Reports Module | eCR |  | OLAP - Configure virtual cubes | 6. Milestone |  | 20 | 0 | 0 | 10 | 30
n | y | All themes | M12 Statistics and Reports Module | eCR |  | OLAP - Optimization | 6. Milestone |  | 10 | 0 | 0 | 10 | 20
n | y | All themes | M12 Statistics and Reports Module | eCR |  | OLAP - Set ACL | 6. Milestone |  | 5 | 0 | 0 | 2 | 7
n | y | All themes | M12 Statistics and Reports Module | eCR |  | Presentation - Create pre-defined reports | 6. Milestone |  | 30 | 0 | 5 | 10 | 45
n | y | All themes | M12 Statistics and Reports Module | eCR |  | Presentation - Configure SSO between Pentaho BI and eCR | 6. Milestone |  | 3 | 0 | 6 | 2 | 11
n | y | All themes | M12 Statistics and Reports Module | eCR |  | Presentation - Integrate Pentaho BI into eCR | 6. Milestone |  | 6 | 5 | 14 | 4 | 29
n | y | Availability | M13 Executive Dashboard Module | OSS |  | Defining key metrics | 6. Milestone |  | 25 | 0 | 0 | 0 | 25
n | y | Availability | M13 Executive Dashboard Module | OSS |  | Data extraction | 6. Milestone |  | 30 | 0 | 10 | 5 | 45
n | y | Availability | M13 Executive Dashboard Module | OSS |  | Configure pre-defined reports | 6. Milestone |  | 5 | 0 | 0 | 3 | 8
n | y | Availability | M13 Executive Dashboard Module | OSS |  | Create management dashboards | 6. Milestone |  | 10 | 5 | 10 | 5 | 30
y | y | Availability |  | OSS | FN45 Digitize paper archive | Document upload | 2. Milestone |  | 6 | 3 | 14 | 3 | 26
y | y | Availability |  | OSS | FN45 Digitize paper archive | List CRs with unorganized documents | 2. Milestone |  | 4 | 1 | 9 | 2 | 16
y | y | Availability |  | OSS | FN45 Digitize paper archive | Change CR for unorganized document | 2. Milestone |  | 4 | 1 | 7 | 2 | 14
y | y | Availability |  | OSS | FN45 Digitize paper archive | Organize document | 2. Milestone |  | 8 | 3 | 20 | 4 | 35
n | y | Availability |  | eCR | FN37 Search Official Gazette | Browse laws | 5. Milestone |  | 7 | 3 | 14 | 4 | 28
n | y | Availability |  | eCR | FN37 Search Official Gazette | Browse news | 5. Milestone |  | 4 | 2 | 9 | 4 | 19
n | y | Availability |  | eCR | FN37 Search Official Gazette | Search laws | 5. Milestone |  | 3 | 1 | 5 | 2 | 11
n | y | Availability |  | eCR | FN37 Search Official Gazette | View laws details | 5. Milestone |  | 8 | 2 | 21 | 4 | 35
n | y | Availability |  | eCR | FN37 Search Official Gazette | View news details | 5. Milestone |  | 3 | 1 | 5 | 2 | 11
n | y | Availability |  | eCR | FN37 Search Official Gazette | Manage personal bookmarks | 5. Milestone |  | 3 | 1 | 5 | 1 | 10
n | y | Availability |  | eCR | FN37 Search Official Gazette | Subscribe for notifications | 5. Milestone |  | 3 | 0 | 6 | 2 | 11
n | y | Availability |  | OSS | 6.4.2.2 Official Gazette | Upload new law | 3. Milestone |  | 9 | 3 | 23 | 4 | 39
n | y | Availability |  | OSS | 6.4.2.2 Official Gazette | Upload amendment or bylaw | 3. Milestone |  | 12 | 4 | 26 | 8 | 50
n | y | Availability |  | OSS | 6.4.2.2 Official Gazette | Upload related news | 3. Milestone |  | 4 | 1 | 8 | 2 | 15
n | y | Availability |  | OSS | 6.4.2.2 Official Gazette | Publish uploaded article | 3. Milestone |  | 3 | 1 | 6 | 1 | 11
n | y | Availability |  | OSS | 6.4.2.2 Official Gazette | List uploaded articles | 3. Milestone |  | 3 | 1 | 7 | 1 | 12
n | y | Availability |  | OSS | 6.4.2.2 Official Gazette | Display article details | 3. Milestone |  | 5 | 2 | 12 | 3 | 22
n | y | Availability |  | OSS | 6.4.2.2 Official Gazette | Unpublished article | 3. Milestone |  | 3 | 1 | 5 | 1 | 10
y | y | Availability |  | OSS | FN50 Keep registered data history | Set-up audit trail framework | 2. Milestone |  | 30 | 0 | 93 | 25 | 148
y | y | Availability |  | OSS | FN50 Keep registered data history | Configure audit trail for UI forms | 2. Milestone |  | 42 | 0 | 56 | 19 | 117
y | y | Availability |  | OSS | FN50 Keep registered data history | List audit trail entries | 2. Milestone |  | 15 | 5 | 30 | 9 | 59
y | y | Availability |  | OSS | FN50 Keep registered data history | View audit trail entry | 2. Milestone |  | 10 | 3 | 28 | 8 | 49
y | y | Availability |  | Data exchange | 7.5.3 Data exchange with NRS (ROP) | Query person's data | 2. Milestone |  | 20 | 0 | 40 | 10 | 70
y | y | Availability |  | Data exchange | 7.5.1 Data exchange with Secretariat General of Taxation | Query CR information | 3. Milestone | FN 9 | Covered by FN9 requirement |  |  |  | 0
y | y | Availability |  | Data exchange | 7.5.1 Data exchange with Secretariat General of Taxation | Query CR financial obligations | 5. Milestone | FN 9 | Covered by FN9 requirement |  |  |  | 0
y | y | Availability |  | Data exchange | 7.5.2 Data exchange with MoMP | Get number of staff | 3. Milestone |  | 12 | 0 | 18 | 5 | 35
y | y | Availability |  | eCR | FN8 CR Search | Query CR | 1. Milestone |  | 6 | 2 | 20 | 2 | 30
y | y | Availability |  | eCR | FN8 CR Search | Display CR information | 1. Milestone |  | 4 | 2 | 14 | 2 | 22
y | y | Availability |  | eCR | FN9 CR Search XML | Query CR information XML | 1. Milestone |  | 25 | 0 | 60 | 15 | 100
y | y | Availability |  | eCR | FN9 CR Search XML | Query CR history XML | 2. Milestone |  | 6 | 0 | 15 | 3 | 24
y | y | Commercial Registration |  | eCR | FN10 New CR | New CR application | 3. Milestone |  | 50 | 5 | 120 | 25 | 200
y | y | Commercial Registration |  | OSS | FN10 New CR | New CR processing - Task list | 3. Milestone |  | 3 | 1 | 10 | 4 | 18
y | y | Commercial Registration |  | OSS | FN10 New CR | New CR processing - Human task forms (10 screens) | 3. Milestone |  | 20 | 4 | 70 | 30 | 124
y | y | Commercial Registration |  | OSS | FN10 New CR | New CR processing - Execution of automated tasks | 3. Milestone |  | 22 | 0 | 35 | 10 | 67
y | y | Commercial Registration |  | OSS | FN10 New CR | New CR processing - Progress monitoring | 3. Milestone |  | 3 | 2 | 8 | 2 | 15
y | y | Update CR |  | eCR | FN11 Change CR Information | Update CR application | 4. Milestone |  | 75 | 7 | 155 | 22 | 259
y | y | Update CR |  | OSS | FN11 Change CR Information | Update CR processing - Task list | 4. Milestone |  | 7 | 2 | 10 | 4 | 23
y | y | Update CR |  | OSS | FN11 Change CR Information | Update CR processing - Human task forms (25 screens) | 4. Milestone |  | 60 | 8 | 180 | 80 | 328
y | y | Update CR |  | OSS | FN11 Change CR Information | Update CR processing - Execution of automated tasks | 4. Milestone |  | 16 | 0 | 35 | 8 | 59
y | y | Update CR |  | OSS | FN11 Change CR Information | Update CR processing - Progress monitoring | 4. Milestone |  | 5 | 2 | 14 | 4 | 25
y | y | Update CR |  | eCR | FN12 Ownership Transfer | Transfer ownership | 5. Milestone |  | 15 | 2 | 25 | 3 | 45
y | y | Update CR |  | eCR | FN13 Liquidation of CR | Initialize liquidation | 5. Milestone |  | 7 | 1 | 14 | 1 | 23
y | y | Update CR |  | eCR | FN13 Liquidation of CR | Cancel CR | 5. Milestone |  | 2 | 1 | 4 | 1 | 8
y | y | Update CR |  | eCR | FN13 Liquidation of CR | Appeal liquidation rejection | 5. Milestone |  | 1 | 0.5 | 4 | 1 | 6.5
y | y | Availability |  | eCR | FN15 Name search | Query Commercial Name | 1. Milestone |  | 2 | 1 | 6 | 1 | 10
y | y | Availability |  | eCR | FN16 My CR | Integrate module-specific portlets | 3. Milestone |  | 4 | 6 | 21 | 3 | 34
y | y | Availability |  | eCR | FN16 My CR | Manage user preferences | 3. Milestone |  | 3 | 3 | 18 | 3 | 27
y | y | Availability |  | eCR | FN16 My CR | Query application status | 1. Milestone |  | 2 | 2 | 13 | 1 | 18
y | y | Availability |  | eCR | FN16 My CR | View application status | 1. Milestone |  | 4 | 10 | 25 | 2 | 41
y | y | Availability |  | Data exchange | 7.5.5 Data exchange with lease contract register (Muscat Municipality) | Query Lease Contract Information | 3. Milestone |  | 12 | 0 | 0 | 0 | 12
y | y | Availability |  | Data exchange | 7.5.5 Data exchange with lease contract register (Muscat Municipality) | Query Addressing System | 3. Milestone |  | 14 | 0 | 0 | 0 | 14
y | y | Availability |  | eCR | FN38 Tasks calendar | View obligations | 4. Milestone |  | 1 | 1 | 9 | 1 | 12
y | y | Availability |  | eCR | FN38 Tasks calendar | Manage calendar notifications channels |  | GR12 | Covered by GR12 requirement |  |  |  | 0
y | y | Availability |  | eCR | FN38 Tasks calendar | Manage calendar representation rights |  | GR12 | Covered by GR12 requirement |  |  |  | 0
y | y | Availability |  | eCR | FN38 Tasks calendar | Register obligations | 4. Milestone |  | 5 | 2 | 15 | 3 | 25
y | y | Availability |  | eCR | FN38 Tasks calendar | Update obligation compliance | 4. Milestone |  | 1 | 1 | 12 | 2 | 16
y | y | Availability |  | OSS | FN47 Task calendar | View obligation list | 4. Milestone |  | 2 | 3 | 10 | 1 | 16
y | y | Availability |  | OSS | FN47 Task calendar | Manage obligation | 4. Milestone |  | 1 | 2 | 4 | 1 | 8
y | y | Availability |  | OSS | FN47 Task calendar | Register obligation service | 5. Milestone |  | 3 | 0 | 10 | 2 | 15
y | y | Availability |  | OSS | FN47 Task calendar | Update obligation compliance service | 5. Milestone |  | 1 | 0 | 7 | 1 | 9
n | y | Update CR | M9 Annual report submission module | eCR | FN14 Submit Annual Report | Submit annual report - XBRL | 6. Milestone |  | 120 | 0 | 170 | 25 | 315
n | y | Update CR | M9 Annual report submission module | eCR | FN14 Submit Annual Report | Submit annual report – Web Form | 6. Milestone |  | 18 | 20 | 70 | 18 | 126
n | y | Update CR | M9 Annual report submission module | eCR | FN14 Submit Annual Report | Submit annual report – Excel | 6. Milestone |  | 24 | 0 | 8 | 4 | 36
n | y | Update CR | M9 Annual report submission module | eCR | FN14 Submit Annual Report | List annual reports | 6. Milestone |  | 3 | 2 | 5 | 1 | 11
n | y | Update CR | M9 Annual report submission module | eCR | FN14 Submit Annual Report | View annual reports | 6. Milestone |  | 3 | 3 | 15 | 2 | 23
n | y | Update CR | M9 Annual report submission module | OSS | FN14 Submit Annual Report | Process annual report | 6. Milestone |  | 12 | 10 | 23 | 2 | 47
n | y | Update CR | M9 Annual report submission module | Data exchange | FN14 Submit Annual Report | Submit annual report service | 6. Milestone |  | 1 | 0 | 4 | 1 | 6
n | y | Update CR | M9 Annual report submission module | Data exchange | FN14 Submit Annual Report | Retrieve annual report service | 6. Milestone |  | 1 | 0 | 4 | 1 | 6
n | y | Availability |  | eCR | FN17 CR statistics | List available reports | 5. Milestone |  | 2 | 1 | 5 | 1 | 9
n | y | Availability |  | eCR | FN17 CR statistics | View statistical report | 5. Milestone |  | 2 | 3 | 12 | 1 | 18
n | y | Availability |  | OSS | FN39 CR Statistics | List pre-defined reports | 5. Milestone |  | 1 | 1 | 8 | 1 | 11
n | y | Availability |  | OSS | FN39 CR Statistics | Manage report authorization | 5. Milestone |  | 1 | 1 | 6 | 2 | 10
y | y | Availability |  | OSS | FN49 My applications |  |  | 6.4.2.1 Licensing, FN10, FN11 | Covered by module-specific "Task list" Ucs |  |  |  | 0
y | y | Update CR |  | eCR | FN26 Register new commercial establishment mortgage | Register Commercial establishment mortgage | 5. Milestone |  | 15 | 3 | 25 | 3 | 46
y | y | Update CR |  | eCR | FN27 Update commercial establishment’s mortgage | Update Commercial establishment mortgage | 5. Milestone | FN11 | Covered in FN11 |  |  |  | 0
y | y | Update CR |  | eCR | FN28 Cancel commercial establishment mortgage | Cancel Commercial establishment mortgage | 5. Milestone | FN11 | Covered in FN11 |  |  |  | 0
y | y | All themes | M10 Meta data module | OSS | 1.2.3.16. Administrative console | Build administrative console | 6. Milestone |  | 15 | 8 | 45 | 15 | 83
n | y | All themes | M12 Statistics and Reports Module | OSS |  | Installation of reporting engine | 2. Milestone |  | 5 | 0 | 15 | 3 | 23
n | y | All themes | M12 Statistics and Reports Module | OSS |  | Integration of reporting engine | 2. Milestone |  | 10 | 0 | 40 | 10 | 60
y | y | All themes | M12 Standard Template Management Module | OSS |  | Upload templates | 5. Milestone
y | y | All themes | M12 Standard Template Management Module | OSS |  | Develop pre-fill rules | 5. Milestone
Note on G82: Peeter Smitt: Only UI development is estimated here.
Note on G86: Peeter Smitt: Only UI development is estimated here.
Note on G127: Peeter Smitt: Re-using notification engine

## Mobile App (hidden)
Theme | Module | Basic | Full | Sub-system | Requirement | Use-case | Milestone | Cross reference | Analysis | UI design | Development | Testing | Total | Grand total
Availability | M1 Public announcements | n | y | Mobile-app | FN28 Search public announcement | List of announcements | 5. Milestone |  | 2 | 2 | 5 | 2 | 11 | Basic | Full
Availability | M1 Public announcements | n | y | Mobile-app | FN28 Search public announcement | A display announcement detail | 5. Milestone |  | 2 | 2 | 5 | 2 | 11 | 166.5 | 672
Licensing | M6 Licence Processing and Management module | n | y | Mobile-app | FN17 Search licence | License/notice simulator | 6. Milestone |  | 10 | 5 | 24 | 5 | 44
Licensing | M6 Licence Processing and Management module | n | y | Mobile-app | FN18 Apply for licence | Apply for license | 6. Milestone |  | 15 | 6 | 52 | 16 | 89
Licensing | M6 Licence Processing and Management module | n | y | Mobile-app | FN18 Apply for licence | Submit notice | 6. Milestone |  | 10 | 4 | 41 | 14 | 69
Licensing | M6 Licence Processing and Management module | n | y | Mobile-app | FN19 My licenses | My licenses | 6. Milestone |  | 4 | 1 | 9 | 3 | 17
Licensing | M6 Licence Processing and Management module | n | y | Mobile-app | FN21 Cancel licence | Cancel license | 6. Milestone |  | 3 | 1 | 7 | 2 | 13
Licensing | M6 Licence Processing and Management module | n | y | Mobile-app | FN17 Search licence | Validate License | 6. Milestone |  | 2 | 1 | 5 | 1 | 9
Licensing | M6 Licence Processing and Management module | y | y | Mobile-app | FN23 ISIC search | ISIC Browser - Browse list | 6. Milestone |  | 1 | 0.5 | 5 | 1 | 7.5
Licensing | M6 Licence Processing and Management module | y | y | Mobile-app | FN23 ISIC search | ISIC Browser - Search list | 6. Milestone |  | 1 | 0.5 | 5 | 1 | 7.5
Licensing | M6 Licence Processing and Management module | y | y | Mobile-app | FN23 ISIC search | ISIC Browser - View related codes | 6. Milestone |  | 2 | 0.5 | 6 | 1 | 9.5
Availability | M8 Trademarks module | n | y | Mobile-app | FN27 Search trademark | Link to WIPO MRS | 4. Milestone |  | 3 | 0.5 | 4 | 1 | 8.5
Availability |  | n | y | Mobile-app | FN30 Search Official Gazette | Search laws | 5. Milestone |  | 3 | 2 | 12 | 3 | 20
Availability |  | n | y | Mobile-app | FN30 Search Official Gazette | Display law text | 5. Milestone |  | 3 | 2 | 6 | 2 | 13
Availability |  | y | y | Mobile-app | C1 OSS Counter Time | OSS counter time | 3. Milestone |  | 4 | 2 | 5 | 3 | 14
Availability |  | y | y | Mobile-app | C2 Fees | Fees | 3. Milestone |  | 4 | 2 | 5 | 3 | 14
Availability |  | y | y | Mobile-app | C3 ITA KIOSK | ITA Kiosk | 3. Milestone |  | 2 | 1 | 5 | 2 | 10
Availability |  | y | y | Mobile-app | C4 SANAD Center | SANAD Centers | 3. Milestone |  | 2 | 1 | 5 | 2 | 10
Availability |  | y | y | Mobile-app | C5 FAQ | FAQ | 3. Milestone |  | 3 | 2 | 8 | 3 | 16
Availability |  | y | y | Mobile-app | C6 MOCI News | MOCI news | 3. Milestone |  | 4 | 2 | 9 | 3 | 18
Availability |  | y | y | Mobile-app | C7 Laws and Regulations | Laws and regulations | 5. Milestone | FN30 | Covered by FN30 requirement |  |  |  | 0
Availability |  | n | y | Mobile-app |  | Identification and authorization | 3. Milestone |  | 6 | 2 | 16 | 4 | 28
Availability |  | n | y | Mobile-app | T1 Application Status Enquiry | Query applications | 2. Milestone |  | 1 | 2 | 14 | 2 | 19
Availability |  | n | y | Mobile-app | T1 Application Status Enquiry | View application status | 2. Milestone |  | 3 | 3 | 10 | 2 | 18
Availability |  | y | y | Mobile-app | T2 Name search | Query Commercial Name | 2. Milestone |  | 1 | 2 | 8 | 1 | 12
Availability |  | y | y | Mobile-app | T3 Check CR validity |  | 5. Milestone | FN7 | Covered by FN7 requirement |  |  |  | 0
Availability |  | y | y | Mobile-app | FN7 CR Search | Query CR | 2. Milestone |  | 4 | 4 | 7 | 2 | 17
Availability |  | y | y | Mobile-app | FN7 CR Search | Display CR information - v2 in 4. Milestone | 2. Milestone |  | 6 | 4 | 19 | 2 | 31
Commercial Registration |  | n | y | Mobile-app | FN9 New CR | New CR application | 5. Milestone |  | 5 | 3 | 20 | 4 | 32
Update CR |  | n | y | Mobile-app | FN10 Change CR Information | Update CR application | 5. Milestone |  | 10 | 3 | 20 | 5 | 38
Update CR |  | n | y | Mobile-app | FN12 Liquidation of CR |  | 5. Milestone | FN10 | Covered by FN10 requirement |  |  |  | 0
Availability |  | n | y | Mobile-app | FN15 My CR | View MyCR information - v2 in 5. milestone | 4. Milestone |  | 17 | 10 | 15 | 7 | 49
Availability |  | n | y | Mobile-app | FN15 My CR | Initialize MyCR services | 5. Milestone |  | 2 | 1 | 12 | 2 | 17

## Website consolidation (hidden)
Basic | Full | # | Functionality | Is the functionality proposed/addressed as part of scope or is it optionally proposed/addressed | Is the proposed functionality included in the cost | Analysis | UI design | Development | Testing | Total | Milestone | Grand total
|  | 1. | Portal General Requirements | [6 empty] | 0 |  | Basic | Full
|  | 1.1. | Design | [6 empty] | 0 |  | 946.5 | 1794.5
y | y | 1.1.1. | MOCI will expect to see at least five sample designs from the winning bidder within ten working days of awarding the work. There is no need to include a sample design with this proposal. However, your portfolio should show previous work of similar scope and size. | Yes | Yes | Included in GR13 estimates |  |  |  | 0
y | y | 1.1.2. | Bidders are also required to work with the other project teams such as the Mobile App Development team and OSS Simplification project team in finalizing themes and look and feel standards for all the planned delivery channels of MOCI. The actual implementation of the finalized themes in their respective project is the responsibility of the respective project team such as OSS Simplification, Mobile App etc. | yes | yes | Included in GR13 estimates |  |  |  | 0
y | y | 1.1.3. | The portal must be multi-lingual and should support Arabic and English. It should be easy to add more languages as and when required with mere configuration changes. | yes | yes | 9 | 0 | 3 | 1 | 13 | 3. Milestone
y | y | 1.1.4. | Visual/textual identity elements highlighting the Government's ownership of the website should be prominently placed on the page. The national identity symbols like Flag, Ministry Logo etc., should be in a proper ratio (not squeezed or stretched) and colour. | Yes | Yes | Included in GR13 estimates |  |  |  | 0
y | y | 1.1.5. | The website should be very flexible and highly configurable. Therefore it is important that the selected bidder should appreciate that virtually all design work – as well as content – should be soft coded. | Yes | Yes | Existing IBM portal and WCM will be used |  |  |  | 0
y | y | 1.1.6. | Although the Portal will be controlled by templates from the Content Management System, the end product – and sample designs – should allow MOCI to show its services and content and should be well balanced and not look crowded | Yes | Yes | Included in GR13 estimates |  |  |  | 0
y | y | 1.1.7. | The user interface design of the Portal has to be done with the following objectives in mind: - Customer navigation should be smooth; - No. of steps to reach for any information should be minimal | Yes | Yes |  |  |  |  | 0
y | y | 1.1.8. | Information Technology Authority maintains certain web development guidelines and standards that ensure consistency in the look and feel of all government portals. Bidders should ensure that the MOCI website complies with these standards. Bidders can refer to www.oman.om and www.business.gov.om to get an understanding of the Template and expectations. | Yes | Yes | Included in GR13 estimates |  |  |  | 0
y | y | 1.2. | The following items should be amply evident from the layout: User oriented; Interactive; Easy to Access | Yes | Yes | Included in GR13 estimates |  |  |  | 0
y | y | 1.2.1. | Each page should have a maximum of three screen scroll length. | Yes | Yes | Included in GR13 estimates |  |  |  | 0
y | y | 1.2.2. | The Portal must be able to operate effectively across all leading browsers and platforms, especially on IE7, Firefox 3.6, Google Chrome 9, Safari 4, Opera 9.5, and later. | Yes | Yes | Included in GR13 estimates |  |  |  | 0
y | y | 1.2.3. | The Portal should also work in all screen resolutions with no white spaces or empty borders. | Yes | Yes | Included in GR13 estimates |  |  |  | 0
n | y | 1.2.4. | The Bidder is expected to ensure that MOCI Portal ranks on the top of the search results by applying appropriate SEO technics. | Yes | Yes | 5 | 0 | 15 | 3 | 23 | 6. Milestone
y | y | 1.2.5. | Alternate text should be provided for all non- text elements (e.g. images). | Yes | Yes | Included in content development |  |  |  | 0
y | y | 1.2.6. | It should be possible to navigate to the home from any page just with a single click. | Yes | Yes | 0 | 1 | 3 | 1 | 5 | 3. Milestone
n | y | 1.2.7. | When printing content, extraneous information such as banners, menus, and footer information should be omitted. Therefore the Portal should provide the functionality to preview and print only the core content of the page upon user request. | Yes | Yes | 4 | 6 | 5 | 1 | 16 | 3. Milestone
n | y | 1.2.8. | The Portal must be able to keep track of the type of visitors accessing the Portal as well as the visitor’s navigation trends within the Portal. Content must then be displayed according to the user’s interests and navigation history. | Yes | Yes | 10 | 2 | 19 | 3 | 34 | 3. Milestone
| y | 1.3. | Content Management System | [6 empty] | 0
y | y | 1.3.1. | The Portal’s content management system should be a web-enabled multi-lingual system. No software should be necessary on Users’ desktop/laptop to populate or update the Portal. | Yes | Yes | Existing IBM portal and WCM will be used |  |  |  | 0
y | y | 1.3.2. | The Portal content management system should support content creation, review, update, approval, authorization and publication processing. | Yes | Yes | 15 | 0 | 10 | 2 | 27 | 3. Milestone
y | y | 1.3.3. | The Portal should provide the Content Management Users with: Onscreen editor, with scope for HTML editing. | Yes | Yes | Existing IBM portal and WCM will be used |  |  |  | 0
y | y | 1.3.4. | All content that the Portal displays should be fed from the Content Management System. | Yes | Yes | All static content comes from WCM |  |  |  | 0
y | y | 1.3.5. | The layout of the content within each page must be controlled by a template. Templates can be created, edited or deleted. When edited, templates can either be saved as a clone of the original or force all pages of that type to update to the new style. The creation of templates must be an easy task (drag and drop functionality is preferable) | Yes | Yes | 25 | 10 | 40 | 10 | 85 | 3. Milestone
y | y | 1.3.6. | The Portal pages must be very well organized and they must not be cluttered with too many links or information. | Yes | Yes | Included in GR13 estimates |  |  |  | 0
y | y | 1.3.7. | Bidders are required to suggest a content structure to MOCI team based on the various target segments of MOCI. Moreover, cross-pollination of content is very important to ensure visitors get the most from the Portal. | Yes | Yes | Included in GR13 estimates |  |  |  | 0
y | y | 1.3.8. | The structure of the Portal content must be completely flexible employing a “tree” structure for the different tiers of information. Being able to add, edit and remove this structure is a privilege that may be granted to content managers only | Yes | Yes | 15 | 0 | 15 | 2 | 32 | 3. Milestone
y | y | 1.3.9. | Pages within the Portal must be able to accept different formats including but not limited to text, video, images, HTML blocks, RSS feeds, presentation slides, Blogs, Banners, etc. | Yes | Yes | Out of the box functionality for WCM |  |  |  | 0
y | y | 1.3.10. | The system should allow for “soft delete” by which deleted documents and publications are not physically removed from the database, but rather flagged as deleted | Yes | Yes | Out of the box functionality for WCM |  |  |  | 0
y | y | 1.3.11. | Depending on the requirements of the different user groups/departments, the Portal might have different CMS processes to manage the content independently as per specific user group’s needs. | Yes | Yes | Out of the box functionality for WCM |  |  |  | 0
y | y | 1.3.12. | The Portal’s CMS should provide multiple authorization levels and different views for different users involved in editing, reviewing and publishing content for MOCI. | Yes | Yes | Out of the box functionality for WCM |  |  |  | 0
y | y | 1.3.13. | Any content that is added to the Portal must be approved first as per a defined set of controls. The Portal must have a workflow mechanism that allows for content to be sent for approval, reviewed, and approved electronically if needed | Yes | Yes | Out of the box functionality for WCM |  |  |  | 0
y | y | 1.3.14. | Authorized content approvers must be able to view a list of content awaiting approval and then be able to accept, reject (with reasons), or edit and then accept each posting. | Yes | Yes | Out of the box functionality for WCM |  |  |  | 0
y | y | 1.3.15. | The Portal must be able to support the deletion and/or archiving of outdated or unwanted content. Also, when published, documents can be set to expire on a certain date and be deleted or archived automatically as desired after they expire. | Yes | Yes | Out of the box functionality for WCM |  |  |  | 0
n | y | 1.3.16. | When an item is archived it must retain its URL but it should be clearly marked as archived. Archived content can only be viewed if the user chooses to view archived documents when navigating or searching. | no | no |  |  |  |  | 0
| y | 1.4. | Really Simple Syndication (RSS) | [6 empty] | 0
n | y | 1.4.1. | Tenderers are required to provide RSS feed functionality so that users can receive updated information regarding important events, news, Bidders published etc as being published in the web site. | Yes | Yes | 5 | 0 | 5 | 2 | 12 | 3. Milestone
| y | 1.5. | Site Map | [6 empty] | 0
y | y | 1.5.1. | The web site should have an up-to-date site map which shows the internal pages of the web site. | Yes | Yes | 2 | 1 | 4 | 1 | 8 | 3. Milestone
y | y | 1.5.2. | The sitemap should provide a hierarchical view of all the pages in the portal to help visitors find specific pages and content easily. | Yes | Yes | Included in previous point |  |  |  | 0
| y | 1.6. | Statistics | [6 empty] | 0
y | y | 1.6.1. | The Portal should be able to general statistical data (and reports) about its visitors and their browsing trends. | Yes | Yes | 3 | 0 | 5 | 3 | 11 | 6. Milestone
| y | 1.7. | Important Links | [6 empty] | 0
n | y | 1.7.1. | The proposed web site should contain a page whereby important links can be displayed for reference for the web site visitors. | Yes | Yes | 3 | 1 | 3 | 1 | 8 | 4. Milestone
n | y | 1.7.2. | The list of links may include the key government agencies and other related agencies. | Yes | Yes | Included in previous point |  |  |  | 0
| y | 1.8. | Website building confidence | [6 empty] | 0
y | y | 1.8.1. | The proposed web site should a Copyright and Privacy Policy prominently displayed on the homepage. | Yes | Yes | 2 | 0.5 | 2 | 0.5 | 5 | 3. Milestone
y | y | 1.8.2. | Website should include comprehensive Terms and Conditions statements, linked from all important pages. | Yes | yes | 3 | 0.5 | 2 | 0.5 | 6 | 3. Milestone
y | y | 1.8.3. | All electronic commerce transactions should be handled using the ITA e-Payment gateway. | Yes | Yes | Included in payment gateway integration |  |  |  | 0
n | y | 1.8.4. | Bidder need to ensure that after appropriate validation by w3c/ or equivalent organizations. Once validations are passed the logo from the respective organization should be positioned and displayed in the website to improve the confidence of visitors. | Yes | Yes | 12 | 4 | 0 | 5 | 21 | 4. Milestone
| y | 1.9. | e-Participation | [6 empty] | 0
| y | 1.9.1. | Surveys And Opinion Polls | [6 empty] | 0
n | y | 1.9.1.1. | Online surveys and opinion polls can be published for e-participation in the web site for visitors. | yes | yes | 9 | 2 | 18 | 3 | 32 | 4. Milestone
n | y | 1.9.1.2. | The administrator of the site should be able to create and publish new surveys and opinion polls and analyse the results of the survey and opinion polls without any software coding. | yes | yes | Included in previous point |  |  |  | 0
n | y | 1.9.1.3. | The website visitors should be able to view the survey/opinion poll results. | Yes | Yes | 4 | 1 | 5 | 2 | 12 | 4. Milestone
n | y | 1.9.1.4. | Forum moderators from MOCI should be assigned to track and monitor different forum discussion groups. | Yes | Yes | 5 | 2 | 9 | 3 | 19 | 4. Milestone
| y | 1.9.2. | Calendar | [6 empty] | 0
n | y | 1.9.2.1. | The web site should contain a calendar of events that is happening within the MOCI. The Calendar should be easy to use and it can be modified easily through the above mentioned content management tool. | Yes | Yes | 6 | 2 | 13 | 2 | 23 | 3. Milestone
| y | 1.9.3. | Discussion Forum | [6 empty] | 0
n | y | 1.9.3.1. | The portal should allow users to initiate discussion in the website | Yes | Yes | 7 | 3 | 19 | 4 | 33 | 4. Milestone
n | y | 1.9.3.2. | The discussion forums may be moderated as per the need. | Yes | Yes | Included in 1.9.1.4. |  |  |  | 0
n | y | 1.9.3.3. | Website administrators should be able to create closed forums targeting a specific set of internal or external users as the participants. | Yes | Yes | 9 | 2 | 21 | 4 | 36 | 4. Milestone
| y | 1.9.4. | Online Forms | [6 empty] | 0
n | y | 1.9.4.1. | The portal should have provision to capture user feedback using online forms and mechanism should be in place to ensure timely response to feedback/queries received through the website. | Yes | Yes | Included in previous points |  |  |  | 0
n | y | 1.9.4.2. | The online form should be developed taking into account the following minimum functionalities:  Verifies entries on client basis (e.g. verify if users wrote their email address in the form)  Provide a list in a form of drop down menu to allow users to direct the query to different departments in the MOCI.  Assign each item/department from the drop down menu to an email address. Allow Web Site Administrator to re-assign the email addresses if required by using the content management tool. | Yes | Yes | Included in previous points |  |  |  | 0
n | y | 1.9.4.3. | The portal should send an acknowledgement note, via email, mobile text message or online message for forms/ emails submitted. | Yes | Yes | 2 | 0 | 6 | 2 | 10 | 4. Milestone
| y | 1.10. | Social Media and Social Networking | [6 empty] | 0
y | y | 1.10.1. | The Portal must support social media and social networking features to engage the users in sharing and socially participating between each other through different channels. There are various avenues to allow social interaction. | Yes | Yes | 2 | 0.5 | 4 | 1 | 7.5 | 3. Milestone
y | y | 1.10.2. | Social link sharing: Portal users should be able to share links to certain Portal content with others through email or through publishing them to popular social media sites. Suitable pages should have links readily available to allow the users to quickly share their favorite content. | Yes | Yes | Included in previous point |  |  |  | 0
n | y | 1.10.3. | Social reviews: Portal users should be able to voice their opinions and reviews on services, places, events and many other aspects in away that is visible and beneficial to all. Other users should be able to read previous reviews and comment on them and even start a discussion around the same topic. | Yes | Yes | 6 | 2 | 16 | 3 | 27 | 3. Milestone
n | y | 1.10.4. | Update alerts: certain pages should have an “update alert” options that allows users to choose to be notified whenever the content of this specific page is updated. | Yes | Yes | 4 | 0 | 9 | 2 | 15 | 3. Milestone
y | y | 1.10.5. | The CMS should be able to activate or deactivate social networking functionalities at the will of the Super Administrator should it be decided in the future that MOCI would refrain from using the social networking tools and applications. | Yes | Yes | 1 | 0 | 3 | 1 | 5 | 3. Milestone
| y | 1.11. | Feedback | [6 empty] | 0
n | y | 1.11.1. | The Portal must have the capability to emphasize and strengthen two-way dialogues and communication between MOCI and the different users. | Yes | Yes | Included in previous points |  |  |  | 0
n | y | 1.11.2. | All pages on the Portal that provide information, instructions, articles or news whether should have a feedback text area allowing the user to enter their remarks and comments. It should be possible to allow only moderated messages as per the need. | Yes | Yes | Included in previous points |  |  |  | 0
n | y | 1.11.3. | The Portal pages should contain a simple opinion poll asking the user to rate how useful they found the page to be. | Yes | Yes | Included in previous points |  |  |  | 0
n | y | 1.11.4. | Remarks and poll results should be forwarded to concerned employees. Also, concerned employees must be able to produce customizable feedback reports and they should be able to send responses to these comments as appropriate. | Yes | Yes | 6 | 3 | 19 | 2 | 30 | 4. Milestone
n | y | 1.11.5. | User feedback must be stored by the Portal to be used later for measuring customer satisfaction and for producing different metrics. | Yes | Yes | 1 | 0 | 5 | 3 | 9 | 4. Milestone
| y | 1.12. | Alerts | [6 empty] | 0
y | y | 1.12.1. | The Portal should provide alert services to its users. Alert services should enable registered users to indicate their interest in some of the information or services provided by the Portal and allow them to register to receive alerts for any updates or additions | Yes | Yes | Included in notification estimates |  |  |  | 0
y | y | 1.12.2. | The Portal should enable customers to receive important alerts through email or SMS to keep them aware about the progress of their e-service request and/or the required actions for the processing of their e-service requests. | Yes | Yes | Included in notification estimates |  |  |  | 0
y | y | 1.12.3. | The Portal should support sending alerts either through email or SMS to registered users. | Yes | Yes | Included in notification estimates |  |  |  | 0
y | y | 1.12.4. | Registered users should also be able to change their preferences regarding what to receive alerts for or how to receive the alerts. | Yes | Yes | Included in notification estimates |  |  |  | 0
y | y | 1.12.5. | The Portal must have the ability to enable/disable SMS notifications. | Yes | Yes | Included in notification estimates |  |  |  | 0
y | y | 1.12.6. | The Portal must support integration with SMS gateway system. | Yes | Yes | Included in notification estimates |  |  |  | 0
y | y | 1.12.7 | MOCI Authorities needs to have an option to choose the list of people to whom the SMS needs to be sent. For example An alert to inform the registered users about a new news item that is published. An alert to inform the Bidders about any new Bidders published etc. | Yes | Yes | Included in notification estimates |  |  |  | 0
| y | 1.13. | Current functionality and information | [6 empty] | 0
y | y | 1.13.1. | In addition to all the new features and functionalities mentioned in this section, bidders are required to replicate the functionalities and information that are available in the site www.moci.gov.om | Yes | Yes | 42 | 10 | 72 | 15 | 139 | 4. Milestone
y | y | 1.13.2. | All the links and functionalities in the current website need to be made available in the new website. Bidder need to submit a document highlighting the current Website functionality to the newly proposed website and get sign off of the same from MOCI team. | Yes | Yes | 25 | 0 | 30 | 10 | 65 | 4. Milestone
y | y | 1.13.3. | Any changes to the functionality and/or information that are available in the current MOCI must be discussed and approved with MOCI prior to implementation. | Yes | Yes | 30 | 0 | 0 | 0 | 30 | 4. Milestone
y | y | 1.13.4. | Bidders are expected to analyse the content and suggest an improved layout considering best practices followed globally. | Yes | Yes | Included in GR13 estimates |  |  |  | 0
| y | 1.14. | Mobile Content | [6 empty] | 0
y | y | 1.14.1. | The website should be displayed correctly on a mobile device. | Yes | Yes | Included in GR13 estimates |  |  |  | 0
n | y | 1.14.2. | There should be an m-GovernmentAgency.gov.om site that should get automatically redirected to when a user accesses the website from a mobile device. For smart phone users the same is not required as currently smart phone browsers has the capability to render normal webpages. | Yes | Yes | 4 | 0 | 5 | 5 | 14 | 4. Milestone
n | y | 1.14.3. | The mobile site should pass the W3C mobile OK checker (http://www.w3.org/TR/mobileOK-basic10-tests/). | Yes | Yes | 10 | 0 | 0 | 5 | 15 | 4. Milestone
| y | 2 | Portal Ministry Specific Requirements Tenderers are required to highlight their experience and showcase and assist MOCI in finalising the full list of sections that MOCI should implement based on the ITA Portal guidelines and Bidders past experience of implementing Portals with other similar organisations. Below is the list of minimum functionalities that MOCI is currently intending and the same will be finalised during the requirement gathering and prototype phase of the project. | [6 empty] | 0
| y | 2.1. | About The Ministry | [6 empty] | 0
y | y | 2.1.1. | The Portal must serve as the single stop gateway for all users looking for:  Information about MOCI.  MOCI Announcements.  Details of the MOCI like The Royal Decree, Ministers Message, and MOCI Policy etc.  Services offered by MOCI and its affiliated organizations. | Yes | yes | 15 | 5 | 0 | 0 | 20 | 4. Milestone
| y | 2.2. | Ministry Programs | [6 empty] | 0
y | y | 2.2.1 | A section to list the details of the various programs related to the MOCI activities. | Yes | Yes | 2 | 1 | 5 | 2 | 10 | 4. Milestone
| y | 2.3 | Organization Hierarchy | [6 empty] | 0
y | y | 2.3.1 | The organization structure should display the hierarchical structure of the MOCI. It should also have the various activities done by the respective section. | yes | yes | 2 | 1 | 5 | 2 | 10 | 4. Milestone
| y | 2.4. | Royal Decrees | [6 empty] | 0
n | y | 2.4.1. | The website should have a section where the Royal Decrees can be published. The site should allow option to highlight the new Decrees and also option to manage the content (add/edit/delete) and also provision to archive etc. | yes | yes | Estimated under Offical Gazette |  |  |  | 0
| y | 2.5. | Royal Orders | [6 empty] | 0
n | y | 2.5.1. | The website should have a section where the Royal Orders can be published. The site should allow option to highlight the new Orders and also option to manage the content (add/edit/delete) and also provision to archive etc. | Yes | Yes | Estimated under Offical Gazette |  |  |  | 0
| y | 2.6. | Laws and Conventions | [6 empty] | 0
n | y | 2.6.1. | The website should have a section where the Laws and Conventions can be published. The site should allow option to highlight the new Laws and Conventions and also option to manage the content (add/edit/delete) and also provision to archive etc. Probably this has dependency on the Official Gazzette module of the eCR portal and vendors need to ensure that duplication is avoided. | Yes | Yes | Estimated under Offical Gazette |  |  |  | 0
| y | 2.7. | Ministerial Committees | [6 empty] | 0
y | y | 2.7.1. | The website should have a section where the details of the various committees and purpose of these committees can be published. The site should allow option to highlight the new committees and also option to manage the content (add/edit/delete) and also provision to archive etc. | Yes | Yes | 2 | 1 | 5 | 2 | 10 | 4. Milestone
y | y | 2.7.2. | There should be also option to upload the photographs of members who are part of these committees and publish the various reports and findings of these committees if needed. | Yes | Yes | 1 | 0 | 4 | 2 | 7 | 4. Milestone
| y | 2.8. | Contact Us Page | [6 empty] | 0
y | y | 2.8.1. | Website should have a 'Contact Us' page, linked from the home page and all relevant places in the website. The complete contact details of important functionaries in the Ministry should be given in the 'Contact Us' section | Yes | Yes | 4 | 2 | 9 | 3 | 18 | 5. Milestone
n | y | 2.8.2. | There should be functionality to interact with the Minister. This should be a blog functionality whereby Minister specific messages can be posted and citizens can participate as well as submit the messages. | Yes | Yes | 5 | 2 | 13 | 4 | 24 | 5. Milestone
y | y | 2.8.3. | Address of the Ministry location with telephone numbers should also be provided. An interactive geographical map (Google map or equivalent) should be provided to locate the address of the Ministry and its regional offices. | Yes | Yes | 4 | 3 | 9 | 2 | 18 | 5. Milestone
y | y | 2.8.4. | Address of the Ministry service providers such as SANAD centers, Lawyer Offices etc should also be listed in the Website. | Yes | Yes | 4 | 1 | 7 | 2 | 14 | 5. Milestone
y | y | 2.8.5. | Bidders should provide a tool to display a Phone Directory which contains contact details of all relevant departments and sections of the MOCI. The functionality should be simple so that it can be maintained easily by the respective section. | Yes | Yes | 5 | 1 | 6 | 2 | 14 | 5. Milestone
| y | 2.9. | NEWS & Press releases | [6 empty] | 0
n | y | 2.9.1. | The Portal should include a news section that displays categorized and searchable news items. Published news items should be related to the MOCI with all its different departments and services. | Yes | Yes | 16 | 4 | 26 | 6 | 52 | 5. Milestone
n | y | 2.9.2. | Announcements of new services, new Portal features, updated regulations or laws, events, conferences or any other type of relevant news should be available within the news section of the Portal. | Yes | Yes | Included in previous point |  |  |  | 0
n | y | 2.9.3. | News items should be searchable by various search criteria. | no | no | Serach will work based on key-word |  |  |  | 0
n | y | 2.9.4. | The news and press releases module need to align its requirements with the functionality “Search Public Announcements” of the Simplified OSS project scope. | no | no | Those will be two different seraches |  |  |  | 0
n | y | 2.9.5. | The homepage of the Portal as well as internal pages should automatically display relevant news headlines and should allow the users to click on them for more details. | Yes | Yes | 3 | 1 | 9 | 2 | 15 | 5. Milestone
n | y | 2.9.6. | News / Press releases should be displayed along with the date and these are organized as per the archival policy of the website | Yes | Yes | 1 | 0 | 3 | 2 | 6 | 5. Milestone
n | y | 2.9.7. | Online news syndication features should also be available on news pages so that interested users can keep up to date with MOCI portal news through their news aggregators. | Yes | Yes | Included in RSS estimates |  |  |  | 0
n | y | 2.9.8. | The site should offer an email distribution of a newsletter | Yes | Yes | 7 | 2 | 12 | 4 | 25 | 5. Milestone
n | y | 2.9.9. | The site should offer a “What’s New” section for providing the recently added/updated details of the site. | Yes | Yes | 6 | 4 | 19 | 6 | 35 | 5. Milestone
| y | 2.10. | e-Services | [6 empty] | 0
y | y | 2.10.1. | As a part of the Oman eGovernment Transformation requirements every ministry website should list the details of all the services provided by the ministry. Therefore the portal should have a page with details of all the services provided by MOCI. | Yes | Yes | Included in each e-service development estimate |  |  |  | 0
y | y | 2.10.2. | There should be a list of most used e-Services of MOCI shown in the Website of MOCI. | Yes | Yes | 2 | 0 | 5 | 2 | 9 | 6. Milestone
n | y | 2.10.3. | There Website should identify automatically the most used e-Services and this section should automatically display the most used eServices link. | Yes | Yes | 2 | 0 | 3 | 1 | 6 | 6. Milestone
y | y | 2.10.4. | It has to be noted that e-Services may have to presented under multiple categories such as Starting a Business, Renewing Business, Licensing etc. | Yes | Yes | Included in GR13 estimates |  |  |  | 0
y | y | 2.10.5. | Considering that MOCI is planning to offer many e-Services as part of the Simplified OSS projects, Bidders are expected to work in coordination with the Simplified OSS development team and come out with a landing page to display all the e-Services offered by MOCI if needed | Yes | Yes | 35 | 0 | 0 | 0 | 35 | 6. Milestone
y | y | 2.10.6. | File and Track complaints. There should also be option to contact the ministry with all the associated contact details. | Yes | Yes | 5 | 1 | 9 | 3 | 18 | 6. Milestone
n | y | 2.10.7. | There should be a service to publish the list of projects currently carried out by MOCI and to update the status of the same. For example opening of OSS in the regions etc. | Yes | Yes | Covered by news functionality |  |  |  | 0
| y | 2.11. | Tender Announcements | [6 empty] | 0
n | y | 2.11.1. | The portal should have a tool to publish Bidders online. The requirement is to publish a list of Bidders which are floated currently and display a maximum of one page summary of the Tender and the way of how to receive the Tender Document. Tenderers are required to provide a link to the E-Tendering web site and specifically to MOCI related Bidders only. | Yes | Yes | 3 | 2 | 7 | 2 | 14 | 5. Milestone
n | y | 2.11.2. | There should be an option to purchase the Tendering documents online by integrating with ITA Payment Gateway. | Yes | Yes | 8 | 2 | 19 | 4 | 33 | 5. Milestone
n | y | 2.11.3. | Mechanism should be in place to ensure that information on old / irrelevant Tender notices is removed or moved into the archive section | Yes | Yes | 1 | 0 | 4 | 1 | 6 | 5. Milestone
| y | 2.12. | eLibrary | [6 empty] | 0
y | y | 2.12.1. | Option to publish and view the catalogue of books that is currently available in MOCI Library. | Yes | Yes | 4 | 2 | 11 | 4 | 21 | 5. Milestone
| y | 2.13. | Photo Gallery, Audio And Video | [6 empty] | 0
y | y | 2.13.1 | The Portal should also host photos and videos related to MOCI. The Portal should have Photo /Video Album functionality using the proposed content management tool. | Yes | Yes | 4 | 2 | 7 | 2 | 15 | 5. Milestone
| y | 2.14. | Job Opportunities | [6 empty] | 0
n | y | 2.14.1. | The web site should contain a job listing facility so that job vacancies can be published online. It should be noted that what is required is just a facility to have another communication channel through the web site especially for jobs advertised by the MOCI. | Yes | Yes | 15 | 3 | 29 | 6 | 53 | 5. Milestone
n | y | 2.14.2. | Mechanism should be in place to ensure that information on old / irrelevant job opening notices is removed or moved into the archive section | Yes | yes | 2 | 0 | 4 | 1 | 7 | 5. Milestone
| y | 2.15. | FAQ | [6 empty] | 0
y | y | 2.15.1. | The proposed web site should show all common queries and their replies related to MOCI. | Yes | yes | 2 | 1 | 9 | 2 | 14 | 5. Milestone
y | y | 2.15.2. | It should be possible to create different sets of FAQs targeted for different user groups of the portal. The portal should automatically display the relevant FAQ based on the user type. | Yes | Yes | 5 | 0 | 12 | 4 | 21 | 5. Milestone
y | y | 2.15.3. | The exact mechanism for the population of actually FAQ content should be agreed with the Documentation team responsible for the “Documentation” sub project. | Yes | Yes | 9 | 0 | 0 | 0 | 9 | 5. Milestone
y | y | 2.15.4. | The process and procedures section also need to be provided a link and the content population for this section need to be carried out in coordination with the “Documentations” sub project team. | yes | yes | 10 | 0 | 0 | 0 | 10 | 5. Milestone
| y | 2.16. | Schemes | [6 empty] | 0
y | y | 2.16.1. | There should be provision to list the various schemes or programs offered by Ministry for various target segments. For example Schemes and programs for SME etc. | yes | yes | 5 | 2 | 7 | 2 | 16 | 5. Milestone
| y | 3 | Portal Non Functional Requirements | [6 empty] | 0
| y | 3.1. | Performance Requirements | [6 empty] | 0
y | y | 3.1.1. | Bidder need to submit an expected portal performance report and justifications | Yes | Yes | 4 | 0 | 2 | 0 | 6 | 6. Milestone
y | y | 3.1.2. | The Bidder should also highlight the data growth expectation based on prior implementation experience. | Yes | Yes | 2 | 0 | 0 | 0 | 2 | 6. Milestone
| y | 3.2. | Scalability Requirements | [6 empty] | 0
y | y | 3.2.1. | Bidders are required to ensure well-balanced load distribution on the various hardware and software components to ensure that no congestion in any of the solution hardware components occurring with the growing load on the Portal. | Yes | Yes | Allready achived by current installation |  |  |  | 0
y | y | 3.2.2. | Bidders are required to clearly specify upgrade path for the solution components (software and hardware) and how the overall solution can handle additional loads. | Yes | Yes | 14 | 0 | 5 | 0 | 19 | 6. Milestone
| y | 3.3. | Integration Requirements | [6 empty] | 0
| y | 3.3.1. | ntegration with ITA Systems Bidders are requested to read the section Current Technology Environment- Other Implementation Details before estimating the effort for the functionalities stated in this section. | [6 empty] | 0
y | y | 3.3.1.1. | The Portal should support online payment and should be possible to integrate with ITA e-payment system(if needed). | Yes | Yes | Included in ITA payment gateway estimates |  |  |  | 0
y | y | 3.3.1.2. | The system should integrate with the Single Sign On (SSO) Functionality offered by the ITA Government Portal. (if needed). | Yes | Yes | Allready done |  |  |  | 0
y | y | 3.3.1.3. | All the public users in the system which needs authentication should make use of ITA Government Portal authentication mechanism. | Yes | Yes | Allraeady done |  |  |  | 0
n | y | 3.3.1.4. | All the services offered by the MOCI Portal should be made available in the ITA Government Portal as well. It should be noted that it is not just redirection that is expected, rather a tight integration between the ITA Government portal and the planned MOCI Portal in the form of Web services, Remote Procedure call, Remote Portlet invocation or appropriate technology based on the platform that is proposed for MOCI Portal. | Yes | Yes | Estimated under MoCI to oman.om bridge |  |  |  | 0
| y | 3.4. | Security | [6 empty] | 0
y | y | 3.5. | The pages of the portal that deal with payment and other critical data should only be accessible via a secured link. | Yes | Yes | 4 | 1 | 9 | 3 | 17 | 3. Milestone
y | y | 3.6. | The following security coding guidelines must be followed:  Do not hard code username/passwords in logs and application code  Do not maintain plain text passwords in configuration files and database  Do not use insecure protocols to exchange data with external parties  Prevent any information leakage through error messages  Shield the system errors and debug information from the end-user which might reveal the technology and product used  Session should expire when no activity or when maximum period has elapsed  Do not put sensitive data in URL parameters  Log all access to sensitive data  Do not rely on client side input validation, always validate input  Check input for cross site scripting (XSS)  Users should not use application credentials to access any system or any database | Yes | Yes | Included in every task estimate |  |  |  | 0
y | y | 3.7. | Ministry may engage a 3rd party organization or ITA Information Security Division to carry out a penetration testing and Bidders are expected to fix any gaps identified as a result. | Yes | Yes | 20 | 0 | 20 | 5 | 45 | 6. Milestone
y | y | 3.8. | The database layers of the implemented solutions should employ user input filtration, user input strong typing, and other security features to prevent SQL injection threats and vulnerabilities. Avoid any dynamic SQL in the implementation which is prone to SQL injection attacks. | Yes | Yes | Included in task estimates |  |  |  | 0
| y | 3.9. | Accessibility | [6 empty] | 0
n | y | 3.9.1. | As the portal is going to be accessed from around the world, from various browsers and operating systems, by people with different abilities and likings, it is imperative that accessibility guidelines are followed as closely as possible. | Yes | Yes | 15 | 10 | 25 | 10 | 60 | 5. Milestone
y | y | 3.9.2. | Functionality of portal should be operable through keyboard. | Yes | Yes | 0 | 0 | 0 | 0 | 0
n | y | 3.9.3 | The site’s content should be read aloud by relevant software | yes | yes | Users need to use own screen readers |  |  |  | 0
y | y | 3.9.4. | The site content should be possible to be resized. | Yes | Yes | Included in GR13 estimates |  |  |  | 0
y | y | 3.9.5. | The site should meet the W3C's Web Content Accessibility Guidelines Priority 1 | Yes | Yes | Included in GR13 estimates |  |  |  | 0
| y | 3.10. | Alternate Content Delivery Channels | [6 empty] | 0
y | y | 3.10.1. | Bidders are expected to ensure that the content that is displayed in the website (like, news, announcements, etc.) can be made available to alternate delivery channels like mobile/tablet etc. as and when required. To enable that, all the content in the portal should be available via a web-service layer. | Yes | Yes | Included in mobile portal estimates |  |  |  | 0
y | y | 3.10.2. | Bidders are required to work with the Mobile App development team to ensure that some of the information contents stated above are made available as Webservice to Mobile App that is planned. | Yes | Yes | 15 | 0 | 0 | 0 | 15 | 5. Milestone
| y | 3.11. | Authentication & Authorization | [6 empty] | 0
y | y | 3.11.1. | As stated earlier, the user Authentication should be done using ITA’s SSO. | Yes | Yes | Included in previous estimates |  |  |  | 0
y | y | 3.11.2. | Users of the Portal should be classified into different categories; These categories are not mutually exclusive as a user can belong to multiple categories at the same time. Some of the categories for MOCI are | Yes | Yes | Included in previous estimates |  |  |  | 0
n | y | 3.11.3. | Provide a customized and targeted experience to users based on their classification and interest. | Yes | Yes | 20 | 0 | 29 | 14 | 63 | 3. Milestone
n | y | 3.11.4. | Each of the Portal sections should categorize its content and services based on various domains or topics that are relevant to the user category of that section. | Yes | Yes | 15 | 0 | 10 | 5 | 30 | 3. Milestone
y | y | 3.11.5. | All sections should have a unified Look & Feel and users of various sections should not feel that they are accessing different Portals. | Yes | Yes | Included in previous estimates |  |  |  | 0
y | y | 3.11.6. | Common Portal functionalities should be shared between the different sections of the Portal and should be accessible to all user types. | Yes | Yes | Included in task estimates |  |  |  | 0
y | y | 3.11.7. | Provide flexible and customizable Portal pages layouts for different sections, the layouts might be different based on the requirements of what needs to be displayed for each type of users. | Yes | Yes | Included in GR13 estimates |  |  |  | 0
y | y | 3.11.8. | There would be fixed elements throughout the pages of the Portal such as the header, footer, navigation links, common Portal functionality and others. For each of the sections, the main parts of the pages would be tailored and customized for the type of users for that section to provide the required content in the most easily accessible and beneficial way to maximize the value of the Portal. | Yes | Yes | Included in GR13 estimates |  |  |  | 0
| y | 3.12. | Development/ Coding | [6 empty] | 0
y | y | 3.12.1. | The new Portal should have a solid yet flexible information architecture and layout. | Yes | Yes | Included in GR13 estimates |  |  |  | 0
y | y | 3.12.2. | For the Portal to be smoothly upgraded/updated in the future, the winning bidder must commit to an open, transparent and annotated method of coding to ensure that they or any other development house can upgrade the Portal easily in the future. | Yes | Yes | Included in task estimates |  |  |  | 0
y | y | 3.12.3. | A very structured and modular approach to coding is required. For example, key site variables should be held in one file, functions and classes of coding must be used instead of replicating lines of code, files and folders should follow a standard naming convention, etc. | Yes | Yes | Included in task estimates |  |  |  | 0
y | y | 3.12.4. | Post the design, development and the audits, the bidder shall hand over the complete code of the Portal applications to MOCI in softcopy format. | Yes | Yes | 15 | 0 | 5 | 0 | 20 | 6. Milestone
y | y | 3.12.5. | Bidder is also required to submit a documentation highlighting the Themes, Style Sheets and various other aspects implemented in the website so that MOCI IT team can take over the future developments or enhancements of the looks and feel ,Themes and functionalities. | Yes | Yes | Included in GR13 estimates |  |  |  | 0
n | y | 3.12.6. | The site should meet the W3C's Web Content Accessibility Guidelines Priority 1 | Yes | Yes | 15 | 0 | 15 | 0 | 30 | 3. Milestone
y | y | 3.12.7. | The website should use latest web technologies like HTML5 and AJAX for partial loading of pages for better user experience and performance. | Yes | Yes | Included in task estimates |  |  |  | 0
y | y | 3.12.8. | Website should use Cascading Style sheets to control layouts/styles and not inline style. | Yes | Yes | Included in GR13 estimates |  |  |  | 0
y | y | 3.12.9. | Labels should be provided when content requires input from the users. | Yes | Yes | Included in task estimates |  |  |  | 0
y | y | 3.12.10. | All input errors should be presented in text. | Yes | Yes | Included in task estimates |  |  |  | 0
y | y | 3.12.11. | Focus should not be trapped in any component while navigating using keyboard. | Yes | Yes | Included in task estimates |  |  |  | 0
y | y | 3.12.12. | Metadata for pages like title, keywords, description and language should be appropriately included | Yes | Yes | Included in GR13 estimates |  |  |  | 0
| y | 4 | Scope of the portal’s Hardware/Hosting Infrastructure. | [6 empty] | 0
y | y | 4.1. | Bidders are required to refer to the Section Hardware Components and Current utilisation section. MOCI do not have plans to procure hardware , however Bidders after analysing the information feels hardware is required the same should be highlighted. | Yes | Yes | Current hardware is enough to take the load |  |  |  | 0
y | y | 4.2. | Bidders are required to ensure that the Website is hosted within the existing private cloud infrastructure at MOCI. | Yes | Yes |  |  |  |  | 0
y | y | 4.3. | The website should be made accessible to the intended audience in an efficient and secure manner on 24 x 7. | Yes | Yes | Existing SLA is used |  |  |  | 0
y | y | 4.4. | The bidder should take all possible secure measures to prevent defacement/ hacking of the website and should have a contingency plan in place for situation like these. | Yes | Yes |  |  |  |  | 0
| y | 5 | Scope of portal’s Maintenance and Support | [6 empty] | 0
| y | 5.1. | General Requirements | [6 empty] | 0
y | y | 5.1.1. | Bidders need to work with the existing Managed services provider at MOCI and ensure that required documentation and details required are transferred to ensure that Maintenance and support can be handled by the existing Managed Operations provider at MOCI. | Yes | Yes | 15 | 0 | 10 | 0 | 25 | 6. Milestone
y | y | 5.1.2. | Bidders are also required to work with existing service provider at MOCI and assist in making any configuration changes or to set up any configuring parameters in order to ensure that performance monitoring and other reporting requirements can be addressed by the existing service provider. | Yes | Yes | 10 | 0 | 10 | 0 | 20 | 6. Milestone
y | y | 5.1.3. | Ensure that upon final acceptance of the MOCI Portal, any OEM warranties will be transferred to MOCI at no additional charge | Yes | Yes | 5 | 0 | 0 | 0 | 5 | 6. Milestone
y | y | 5.1.4. | Ensure that all warranty, maintenance & support documentation (whether expired or not) will be delivered to MOCI at the issuance of the final acceptance certificate. | Yes | Yes | 5 | 0 | 0 | 0 | 5 | 6. Milestone
y | y | 5.1.5. | Bidders are required to provide Premium Level warranty and support through the technology Bidder for all software used in the MOCI Portal. | Yes | Yes | Included on overall project warranty |  |  |  | 0
y | y | 5.1.6. | Bidders’ warranty must cover all work activities contained in the contract against all design, manufacturing, and environment faults until the issuance of the final acceptance. | Yes | Yes | Included on overall project warranty |  |  |  | 0
| y | 5.2. | Warranty Requirements | [6 empty] | 0
y | y | 5.2.1. | The duration of the warranty shall be mandatory for 3 months from the final acceptance date of the MOCI Portal and Bidder need to fix any fugs or issues in the Website. | Yes | Yes | Included on overall project warranty |  |  |  | 0
y | y | 5.2.2. | The warranty shall include the repair or replacement of the products / components during the support period by the Bidder. The replacement products / components shall meet the related specifications without further repair or modification. | Yes | Yes | Included on overall project warranty |  |  |  | 0
y | y | 5.2.3. | Bidders shall be liable for all costs including, but not limited to, the costs of material, labor, travel, transport and living expenses associated with the collection and return of the components covered by the warranty, maintenance & support | Yes | Yes | Included on overall project warranty |  |  |  | 0
y | y | 5.2.4 | Bidders shall work with the existing Managed Operations team at MOCI and ensure that Appropriate SLA in line with the existing ones for the One Stop Shop system is defined and configured. | Yes | Yes | Included on overall project warranty |  |  |  | 0
| y | 6 | Scope of Knowledge Transfer and Training | [6 empty] | 0
| y | 6.1. | General Requirements | [6 empty] | 0
y | y | 6.2. | Bidder shall submit its proposed plan and approach for conducting the knowledge transfer and training across MOCI to delivering the required knowledge. | Yes | Yes | Included in training estimates |  |  |  | 0
y | y | 6.3. | Bidder is expected to transfer knowledge and train these staff to ensure that the system can be maintained effectively after the exit of the bidder. | Yes | Yes | Included in training estimates |  |  |  | 0
y | y | 6.4. | Ensure source code of all software components developed or customized during the implementation of the entire solution must be handed over to MOCI after project completion | Yes | Yes |  |  |  |  | 0
y | y | 6.5. | Bidders are required to provide knowledge transfer and training for the Website, CMS, Themes, CSS and other components throughout the project implementation phases covering various users groups. | Yes | Yes | Included in training estimates |  |  |  | 0
y | y | 6.6. | All proposed trainings must be delivered at MOCI premises and must be classroom-based and instructor-led. | Yes | Yes | Included in training estimates |  |  |  | 0
y | y | 6.7. | Online / Remote presentations (e.g. WebEx sessions or the like) will not be accepted as part of the official training program. | Yes | Yes | No WebEx trainings are included for web-site consolidation project |  |  |  | 0
y | y | 6.8. | Bidders are required to discuss the training approach, courses, sessions and tools to be used to support the training and knowledge transfer | Yes | Yes | 20 | 0 | 0 | 0 | 20 | 2. Milestone
n | y | 6.9. | Bidders are required to handle all training activities including but not limited to the provision of training venue, site set-up, PCs, training material, standard office supplies and any other support tasks as required to ensure successful training | no | no | Venue, PC, office supplies, transportation have to be provided by client |  |  |  | 0
y | y | 6.10. | Bidders will also be required to provide electronic and hard copies of all training materials used during training sessions. All training courses are required to be by certified / authorized trainers. | Yes | Yes |  |  |  |  | 0
y | y | 6.11. | Bidders are required to specify and describe the training courses / sessions they will provide according to the template provided in Annexure I. | Yes | Yes | Included in training estimates |  |  |  | 0
y | y | 6.12. | Bidders are required to define the skills and expertise needed to maintain, support and undertake future enhancements. | Yes | Yes | Included in training estimates |  |  |  | 0
| y | 7.1. | Scope of work of Project Implementation and Project Management | [6 empty] | 0
y | y | 7.1.1. | Bidders are required to provide their requirements for on-site project implementation from MOCI premises where the project scope will be developed, tested and deployed | Yes | Yes | 15 | 0 | 0 | 0 | 15 | 2. Milestone
y | y | 7.1.2. | Bidder to provide the approximate physical space and setup required by the Bidder’s project team during the various phases of this project. | Yes | Yes | 5 | 0 | 0 | 0 | 5 | 2. Milestone
Note on D116: Peeter Smitt: Integration with MoCI twitter account
Note on D168: Peeter Smitt: Top 10 used services will be made available

## Data cleansing (hidden)
Basic | Full | Milestone | Activity | Project managment | Data analyst | Development | Testing | Total | Grand total
y | y | 1. Milestone | ROP Integration | 15 | 5 | 35 | 5 | 60 | Basic | Full
y | y |  | Identification and removal of manual data entry fields in the existing system | Efforts under GR1 in general tasks |  |  |  | 0 | 230 | 375
y | y | 1. Milestone | Preparation of environment | 10 | 10 | 15 | 0 | 35
y | y | 1. Milestone | Development of Query | 10 | 35 | 20 | 15 | 80
n | y | 1. Milestone | Development OCR | 15 | 15 | 80 | 35 | 145
y | y | 2. Milestone | Execution of scripts and roll-out | 10 | 20 | 10 | 0 | 40
y | y | 2. Milestone | Analysis and Final Report preparation | 5 | 10 | 0 | 0 | 15 | Not included in price!

## Documentation (hidden)
Full
Area | Total number of documents estimated | Creation | Collection | Translation | Total effort | % per Milestone | 1. Milestone | 2. Milestone | 3. Milestone | 4. Milestone | 5. Milestone | 6. Milestone |  | Eff per milestone | 1. Milestone | 2. Milestone | 3. Milestone | 4. Milestone | 5. Milestone | 6. Milestone
Laws and regulations | Estimated under business consultancy |  |  |  | 0 | [7 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0
Processes and procedures | Estimated under business consultancy |  |  |  | 0 | [7 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0
FAQ | 100 | 25 | 0 | 15 | 40 |  |  |  | 10% | 10% | 40% | 40% | 100% |  | 0 | 0 | 4 | 4 | 16 | 16
User Manual | 500 | 300 | 50 | 200 | 550 |  |  |  |  | 10% | 30% | 60% | 100% |  | 0 | 0 | 0 | 55 | 165 | 330
Polices | Estimated under business consultancy |  |  |  | 0 | [7 empty] | 0% |  | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | Total | 0 | 0 | 4 | 59 | 181 | 346
Basic
Area | Total number of documents estimated | Creation | Collection | Translation | Total effort | [8 empty] | Eff per milestone | 1. Milestone | 2. Milestone | 3. Milestone | 4. Milestone | 5. Milestone | 6. Milestone
Laws and regulations | Estimated under business consultancy |  |  |  | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Processes and procedures | Estimated under business consultancy |  |  |  | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
FAQ | 50 | 10 | 0 | 5 | 15 | [9 empty] | 0 | 0 | 1.5 | 1.5 | 6 | 6
User Manual | 250 | 150 | 30 | 100 | 280 | [9 empty] | 0 | 0 | 0 | 28 | 84 | 168
Polices | Estimated under business consultancy |  |  |  | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | Total | 0 | 0 | 1.5 | 29.5 | 90 | 174
Grand total
[14 empty] | Basic | Full
[14 empty] | 295 | 590

## Trainings (hidden)
Basic | Full |  |  | Milestone | Participants | Cost per participant | Total cost
y | y | BPM | BPM1 | 5. Milestone | 5 | 1200 | 6000
y | y | Rule engine | Drools1 | 5. Milestone | 5 | 900 | 4500
n | y | Orbeon | Orbeon1 | 6. Milestone | 10 | 900 | 9000
n | y | Pentaho | SLN4000 | 6. Milestone | 5 | 770 | 3850
n | y | Pentaho | SLN6000 | 6. Milestone | 5 | 500 | 2500
n | y | Pentaho | SLN3000 | 6. Milestone | 5 | 250 | 1250
n | y | Pentaho | PDI2000 | 6. Milestone | 5 | 1000 | 5000
n | y | Pentaho | ADM2050 | 6. Milestone | 5 | 500 | 2500
y | y | Open topic | Open1 | 6. Milestone | 10 | 1200 | 12000
y | y | IBM WCM | WCM1 | 4. Milestone | 10 | 1400 | 14000
y | y | Overview of transformed OSS | RIK2014_1 | 6. Milestone | 100 | 50 | 5000
y | y | Commercial registration for name verifiers | RIK2014_2 | 4. Milestone | 10 | 50 | 500
y | y | Commercial registration for editors | RIK2014_3 | 4. Milestone | 5 | 50 | 250
y | y | Commercial registration for verifiers and advisors | RIK2014_4 | 4. Milestone | 30 | 250 | 7500
n | y | Changes in licencing | RIK2014_5 | 5. Milestone | 60 | 150 | 9000
n | y | Training of business analysts | RIK2014_6 | 4. Milestone | 3 | 800 | 2400
y | y | Training of senior management | RIK2014_7 | 4. Milestone | 10 | 120 | 1200
n | y | Training of business process owners | RIK2014_8 | 4. Milestone | 50 | 150 | 7500
y | y | Training of support service providers | RIK2014_9 | 4. Milestone | 10 | 200 | 2000
n | y | Management trainings | RIK2014_10 | 5. Milestone | 4 | 2500 | 10000
y | y | Training of trainers | RIK2014_11 | 5. Milestone | 25 | 250 | 6250
n | y | Training of service providers and representatives of OCCI and SME | RIK2014_12 | 6. Milestone | 150 | 50 | 7500
Totals | [6 empty] | 119700

## Utility sheet (hidden)
Sub-system to FN mapping
OSS | Estimated effort | eCR | Estimated effort | mobileApp | Estimated effort | Data exchange | Estimated effort | General | Estimated effort
FN39 CR Statistics | 21 | FN8 CR Search | 52 | C1 OSS Counter Time | 14 | 7.5.1 Data exchange with Secretariat General of Taxation | 0 | GR1 Remove Manual Investor Data Entry | 173 | Module list | OSS Simplification Total effort
FN40 Report debt | 14 | FN9 CR Search XML | 124 | C2 Fees | 14 | 7.5.2 Data exchange with MoMP | 35 | GR2 Matching Business Rules | 105 | M1 Public announcements | 169
FN41 Search debt | 33 | FN10 New CR | 424 | C3 ITA KIOSK | 10 | 7.5.3 Data exchange with NRS (ROP) | 70 | GR3 Reusability | 75 | M2 Information management module | 0
FN42 Trademark search | 17 | FN11 Change CR Information | 694 | C4 SANAD Center | 10 | 7.5.4 Data exchange with trademark register (MOCI Trademark Department) | 0 | GR4 Code Compliance principles | 0 | M3 Communication and notification module | 151
FN43 Publish an announcement | 68 | FN12 Ownership Transfer | 45 | C5 FAQ | 16 | 7.5.5 Data exchange with lease contract register (Muscat Municipality) | 26 | GR5 Code Compliance Report | 5 | M4 Licence requirements management module(ISIC classification) | 340
FN44 Search public announcement | 9 | FN13 Liquidation of CR | 37.5 | C6 MOCI News | 18 | 7.5.6 Data exchange with debt register | 58 | GR6 Interface Compliance | 0 | M5 Classification management module | 0
FN45 Digitize paper archive | 91 | FN14 Submit Annual Report | 570 | C7 Laws and Regulations | 0 | 7.5.7 Data exchange with different registers regarding licenses | 74 | GR7 Code Documentation | 0 | M6 Licence Processing and Management module | 1251
| 0 | FN15 Name search | 10 | T1 Application Status Enquiry | 37 |  | 0 | GR8 System Documentation | 1155 | M7 Debt module | 143
FN47 Task calendar | 48 | FN16 My CR | 120 | T2 Name search | 12 |  |  | GR9 Interface Compliance Checks | 10 | M8 Trademarks module | 25.5
FN49 My applications | 0 | FN17 CR statistics | 27 | T3 Check CR validity | 0 |  |  | GR10 Web Service Support | 0 | M9 Annual report submission module | 570
FN50 Keep registered data history | 373 | FN18 Search licence | 0 | FN7 CR Search | 48 |  |  | GR11 Single Sign On | 0 | M10 Meta data module | 83
6.4.2.1 Licensing | 1142 | FN19 Search licence XML | 0 | FN9 New CR | 32 |  |  | GR12 Authorization and Delegation | 101.5 | M11 Standard Template Management Module | 0
6.4.2.2 Official Gazette | 159 | FN20 Apply for licence/notice of economic activities | 174 | FN10 Change CR Information | 38 |  |  | GR13 Screen Navigation | 305 | M12 Statistics and Reports Module | 508
|  | FN21 My licences | 20 | FN12 Liquidation of CR | 0 |  |  | GR14 Testing | 365 | M13 Executive Dashboard Module | 108
|  | FN22 Modify licence/notice of economic activities | 76 | FN14 Name search (version2) | 0 |  |  | FN1 PKI authentication | 0
|  | FN23 Cancel licence/notice of economic activities | 16 | FN15 My CR | 66 |  |  | FN2 PKI electronic signature | 110 | Sub-system list
|  | FN24 Licence statistics | 22 | FN17 Search licence | 53 |  |  | FN3 Automated checks | 245 | eCR
|  | FN25 ISIC search | 27 | FN18 Apply for licence | 158 |  |  | FN4 Electronic stamp | 71 | OSS
|  | FN26 Register new commercial establishment mortgage | 46 | FN19 My licenses | 17 |  |  | FN5 Payment calculator | 0 | Mobile-app
|  | FN27 Update commercial establishment’s mortgage | 0 | FN21 Cancel licence | 13 |  |  | FN6 Payment statistics | 152 | Data exchange
|  | FN28 Cancel commercial establishment mortgage | 0 | FN23 ISIC search | 24.5 |  |  | FN7 Submit refund application | 91
|  | FN29 Search debt | 15 | FN27 Search trademark | 8.5 |  |  | 3.3.1.4 MoCI to oman.om bridge | 70
|  | FN30 Report debt | 7.5 | FN28 Search public announcement | 22
|  | FN31 Cancel debt | 15.5 | FN30 Search Official Gazette | 33
|  | FN32 Search trademark | 8.5
|  | FN33 Search trademark XML | 0
|  | FN34 Search public announcement | 33
|  | FN35 Search public announcement XML | 15
|  | FN36 Publish public announcement | 9
|  | FN37 Search Official Gazette | 125
|  | FN38 Tasks calendar | 53

## Effort per project (hidden)
| Basic option | [5 empty] | Full option
Project | Analysis | UI design | Development | Testing | Total | chksum | Analysis | UI design | Development | Testing | Total | chksum
Simplified OSS | 1140 | 218 | 2411 | 743 | 4512 | 0 | 2577 | 416.5 | 4628 | 1341 | 8962.5 | 0
Mobile Application | 34 | 21.5 | 87 | 24 | 166.5 | 0 | 135 | 72 | 364 | 101 | 672 | 0
Website consolidation | 443 | 47.5 | 364 | 92 | 946.5 | 0 | 689 | 107.5 | 783 | 215 | 1794.5 | 0
Data cleansing | 50 | 80 | 80 | 20 | 230 | 0 | 65 | 95 | 160 | 55 | 375 | 0
Documentation | 0 | 0 | 0 | 295 | 295 | 0 | 0 | 0 | 0 | 590 | 590 | 0
|  |  |  | Total | 6150 |  |  |  |  | Total | 12394

## Effort per role (hidden)
MM/MD rate | 21.67
|  | Basic option |  | Full option
Project | Role | Effort (md) | Effort (mm) | Effort (md) | Effort (mm)
Simplified OSS
| Project manager | 456 | 21.0429 | 1030.8 | 47.5681
| System analyst | 684 | 31.5644 | 1546.2 | 71.3521
| UX designer | 218 | 10.06 | 416.5 | 19.2201
| Architect | 723.3 | 33.3779 | 1388.4 | 64.0701
| Developer | 1687.7 | 77.8819 | 3239.6 | 149.497
| QA Specialist | 743 | 34.287 | 1341 | 61.8828
Sub-total project |  | 4512 |  | 8962.5
Mobile application
| Project manager | 13.6 | 0.6276 | 54 | 2.4919
| System analyst | 20.4 | 0.94139 | 81 | 3.7379
| UX designer | 21.5 | 0.99216 | 72 | 3.3226
| Architect | 26.1 | 1.2044 | 109.2 | 5.0392
| Developer | 60.9 | 2.8103 | 254.8 | 11.7582
| QA Specialist | 24 | 1.1075 | 101 | 4.6608
Sub-total project |  | 166.5 |  | 672
Website consolidation
| Project manager | 177.2 | 8.1772 | 275.6 | 12.718
| System analyst | 265.8 | 12.2658 | 413.4 | 19.0771
| UX designer | 47.5 | 2.192 | 107.5 | 4.9608
| Architect | 109.2 | 5.0392 | 234.9 | 10.8399
| Developer | 254.8 | 11.7582 | 548.1 | 25.293
| QA Specialist | 92 | 4.2455 | 215 | 9.9216
Sub-total project |  | 946.5 |  | 1794.5
Data cleansing
| Project manager | 50 | 2.3073 | 65 | 2.9995
| Data analyst | 80 | 3.6917 | 95 | 4.3839
| Developer | 80 | 3.6917 | 160 | 7.3835
| QA Specialist | 20 | 0.92293 | 55 | 2.5381
Sub-total project |  | 230 |  | 375
Documentation
| Technical writer | 295 | 13.6133 | 590 | 27.2266

## Milestone breakdown (hidden)
Full option
| 1. Milestone | 2. Milestone | 3. Milestone | 4. Milestone | 5. Milestone | 6. Milestone | Total | Chksum
Project | Effort (mandays)
Simplified OSS | 869.5 | 1669 | 1506.5 | 1695 | 1591.5 | 1631 | 8962.5 | 0
Analysis | 221 | 511 | 420 | 384 | 459 | 582
UI Design | 77.5 | 68 | 63.5 | 65 | 66.5 | 76
Development | 417 | 835 | 823 | 969 | 827 | 757
Testing | 154 | 255 | 200 | 277 | 239 | 216
Chksum | 0 | 0 | 0 | 0 | 0 | 0
Business consultancy | 137 | 501 | 578 | 421 | 75 | 0 | 1712 | 0
TO-BE process | 25 | 186 | 256 | 123 | 50 | 0
Change management | 67 | 182 | 184 | 118 | 15 | 0
Legal | 17 | 33 | 50 | 44 | 5 | 0
Follow-up/PM | 28 | 100 | 88 | 136 | 5 | 0
Chksum | 0 | 0 | 0 | 0 | 0 | 0
Mobile Application | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -672
Analysis | 0 | 0 | 0 | 0 | 0 | 0
UI Design | 0 | 0 | 0 | 0 | 0 | 0
Development | 0 | 0 | 0 | 0 | 0 | 0
Testing | 0 | 0 | 0 | 0 | 0 | 0
Chksum | 0 | 0 | 0 | 0 | 0 | 0
Website consolidation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1794.5
Analysis | 0 | 0 | 0 | 0 | 0 | 0
UI Design | 0 | 0 | 0 | 0 | 0 | 0
Development | 0 | 0 | 0 | 0 | 0 | 0
Testing | 0 | 0 | 0 | 0 | 0 | 0
Chksum | 0 | 0 | 0 | 0 | 0 | 0
Data cleansing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -375
Project management | 0 | 0 | 0 | 0 | 0 | 0
Data analysis | 0 | 0 | 0 | 0 | 0 | 0
Development | 0 | 0 | 0 | 0 | 0 | 0
Testing | 0 | 0 | 0 | 0 | 0 | 0
Chksum | 0 | 0 | 0 | 0 | 0 | 0
Documentation | 0 | 0 | 4 | 59 | 181 | 346 | 590 | 0
Total effort | 1006.5 | 2170 | 2088.5 | 2175 | 1847.5 | 1977 | 11264.5 |  | Early bird discount | 19999
| Price(OMR) | [7 empty] | DRUG Payment schedule
Simplified OSS | 319124.3333 | 577559.8333 | 506605.3333 | 596861.8333 | 571613.3333 | 607972.8333 | 3179737.5 |  | Downpayment | 10%
Analysis | 88671.7083 | 206121.7083 | 169266.7083 | 154686.7083 | 185061.7083 | 234876.7083
UI Design | 21719.2083 | 18954.7083 | 17645.2083 | 18081.7083 | 18518.2083 | 21282.7083
Development | 132606.7083 | 266366.7083 | 262526.7083 | 309246.7083 | 263806.7083 | 241406.7083
Testing | 43826.7083 | 73116.7083 | 57166.7083 | 79496.7083 | 68476.7083 | 61806.7083
Licenses | 32300 | 13000 | 0 | 0 | 0 | 0
Trainings | 0 | 0 | 0 | 35350 | 35750 | 48600
Business consultancy | 54910 | 198627 | 228202 | 167676 | 29225 | 0 | 678640 |  | Requirements | based on estimates
TO-BE process | 9550 | 71052 | 97792 | 46986 | 19100 | 0
Change management | 27135 | 73710 | 74520 | 47790 | 6075 | 0
Legal | 6885 | 13365 | 20250 | 17820 | 2025 | 0
Follow-up/PM | 11340 | 40500 | 35640 | 55080 | 2025 | 0
Mobile Application | 0 | 31610 | 36377 | 19555.5 | 46700 | 87154.5 | 221397 |  | UAT | based on estimates
Analysis | 0 | 6075 | 10125 | 8100 | 10935 | 19440
UI Design | 0 | 4365 | 3492 | 3055.5 | 4365 | 5674.5
Development | 0 | 18560 | 16960 | 6080 | 25600 | 49280
Testing | 0 | 2610 | 5800 | 2320 | 5800 | 12760
Website consolidation | 0 | 16200 | 158796.5 | 182631 | 174399 | 91211 | 623237.5 |  | Go-Live | 10%
Analysis | 0 | 16200 | 66015 | 77355 | 61965 | 57510
UI Design | 0 | 0 | 7711.5 | 10476 | 12804 | 291
Development | 0 | 0 | 69120 | 73920 | 79040 | 28480
Testing | 0 | 0 | 15950 | 20880 | 20590 | 4930
Data cleansing | 103115 | 13070 | 0 | 0 | 0 | 0 | 116185
Project management | 20250 | 6075 | 0 | 0 | 0 | 0
Data analysis | 18915 | 8730 | 0 | 0 | 0 | 0
Development | 48000 | 3200 | 0 | 0 | 0 | 0
Testing | 15950 | 0 | 0 | 0 | 0 | 0
Deduction |  | -4935
Documentation | 0 | 0 | 1160 | 17110 | 52490 | 100340 | 171100 |  | Trainings Payment schedule
Totalper milestone | 477149.3333 | 837066.8333 | 931140.8333 | 983834.3333 | 874427.3333 | 886678.3333 | 4990297 |  | Downpayment | 10%
[9 empty] | After Delivery | 90%
| Payment milestones | [7 empty] | Licenses Payment schedule
Simplified OSS | [8 empty] | Downpayment | 10%
Downpayment | 28682.4333 | 56455.9833 | 50660.5333 | 56151.1833 | 53586.3333 | 55937.2833 | 301473.75 |  | After Delivery | 90%
Requirements | 88312.7333 | 180061.1333 | 149529.5333 | 138214.7333 | 162863.9333 | 204927.5333
UAT | 141146.7333 | 271586.7333 | 255754.7333 | 310994.7333 | 265826.7333 | 242570.7333 |  |  | Business consultancy payment schedule
Go-live | 28682.4333 | 56455.9833 | 50660.5333 | 56151.1833 | 53586.3333 | 55937.2833 |  |  | Downpayment | 10%
Trainings | [8 empty] | TOBE sign-off | based on estimates
Downpayment | 0 | 0 | 0 | 3535 | 3575 | 4860 | 11970 |  | Change managment report sign-off | based on estimates
After delivery | 0 | 0 | 0 | 31815 | 32175 | 43740 |  |  | Follow-up report sign-off | 10%
Licenses
Downpayment | 3230 | 1300 | 0 | 0 | 0 | 0 | 4530 |  | Documentation payment schedule
After delivery | 29070 | 11700 | 0 | 0 | 0 | 0 |  |  | Downpayment | 10%
Business consultancy | [8 empty] | After Delivery | 90%
Downpayment | 5491 | 19862.7 | 22820.2 | 16767.6 | 2922.5 | 0 | 67864
TOBE sign-off | 14791.5 | 75975.3 | 106237.8 | 58325.4 | 19012.5 | 0
Change management report sign-off | 24421.5 | 66339 | 67068 | 43011 | 5467.5 | 0
Follow-up report sign-off | 10206 | 36450 | 32076 | 49572 | 1822.5 | 0
Mobile Application
Downpayment | 0 | 3161 | 3637.7 | 1955.55 | 4670 | 8715.45 | 22139.7
Requirements | 0 | 8352 | 10893.6 | 8924.4 | 12240 | 20091.6
UAT | 0 | 16936 | 18208 | 6720 | 25120 | 49632
Go-Live | 0 | 3161 | 3637.7 | 1955.55 | 4670 | 8715.45
Website Consolidation
Downpayment | 0 | 1620 | 15879.65 | 18263.1 | 17439.9 | 9121.1 | 62323.75
Requirements | 0 | 14580 | 58981.2 | 70264.8 | 59815.2 | 46240.8
UAT | 0 | 0 | 68056 | 75840 | 79704 | 26728
Go-Live | 0 | 0 | 15879.65 | 18263.1 | 17439.9 | 9121.1
Data Cleansing
Downpayment | 11618.5 | 0 | 0 | 0 | 0 | 0 | 11618.5
Requirements | 46474 | 0 | 0 | 0 | 0 | 0
UAT | 0 | 46474 | 0 | 0 | 0 | 0
Go-Live | 0 | 11618.5 | 0 | 0 | 0 | 0
Documentation
Downpayment | 0 | 0 | 17110 | 0 | 0 | 0 | 17110
After delivery | 0 | 0 | 0 | 0 | 0 | 153990
Total | 432126.8333 | 882089.3333 | 947090.8333 | 966724.3333 | 821937.3333 | 940328.3333
Downpayment total | 49021.9333 | 82399.6833 | 110108.0833 | 96672.4333 | 82193.7333 | 78633.8333
| 11.34% | 9.341% | 11.63% | 10% | 10% | 8.362%
Downpayment | 49021.9333 | 82399.6833 | 110108.0833 | 96672.4333 | 82193.7333 | 78633.8333
Note on A38: Peeter Smitt: Early bird discount is equaly detucted from each payment (1/24 from each one)

## Resource Planner
This document is a property of Digital Transformation PMO at Ministry of Technology and Communications. These guidance has been developed based on the expertise and involvement of the PMO Members in Various Digital Transformation Projects. No part of these checklist may be reproduced or transmitted in any form or by any means, electronic or mechanical, including photocopying, recording or by any information storage and retrieval system, without permission in writing from Digital Transformation PMO.
[6 empty] | Milestone 1 |  |  |  | Milestone 2 |  |  |  | Milestone 3 |  |  |  | Milestone 4 |  |  |  | Milestone 5 |  |  |  | Milestone 6
[6 empty] | L1 | L2 | L3 | L4 | L5 | L6 | L7 | L8 | L9 | L10 | L11 | L12 | L13 | L14 | L15 | L16 | L17 | L18 | L19 | L20 | L21 | L22 | L23 | L24
Work Groups | Projects | Team | Ministry personnel per role per milestone | Ministry Specialists Name | WG Leader
Project coordination | All Projects | Project coordination team | Project coordination team member | [26 empty] | 0 | bar: Milestone 1 L1 to Milestone 6 L24
| Transformation Project, Mobile App, Website consolidation, Data Cleansing |  | System owner | bar: Milestone 1 L1 to Milestone 6 L24
| All Projects |  | Business domain expert | bar: Milestone 2 L5 to Milestone 6 L24
General tasks | bar: Milestone 1 L1 to Milestone 3 L12
[14 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x
Business Users | bar: Milestone 1 L1 to Milestone 2 L8
External Ministry
Add all the modules
The work Groups can be defined based on the Project Governance Structure Defined for the project